## Major Projects
Corporate Services
2015 MAJOR PROJECTS
Overview
Team | Project | Project Manager | Project Type | Progress | Proposed Rating | Target Date | Days Left | % Complete | Dashboard
Human Resources | Project Team Goals | M. Tse-Gonzalez | Major | Target | Meets | 2015-10-31 | -1254 | 30%
Human Resources | Career Pathing | N. Rivera-Mendez | Major | Target | Meets | 2015-10-31 | -1254 | 60%
Human Resources | Officer Criteria | M. Tse-Gonzalez | Major | Target | Meets | 2015-10-31 | -1254 | 10%
Human Resources | Recognition Award Program | N. Rivera-Mendez | Major | Target | Meets | 2015-10-31 | -1254 | 50%
Human Resources | Continuing Professional Education | N. Rivera-Mendez | Major | Target | Meets | 2015-10-31 | -1254 | 40%
Human Resources | Employee Wellness | M. Sanders | Major | Target | Meets | 2016-01-01 | -1192 | 0%
Facilities Services | Real Estate Program | E. Gonzalez | Major | Target | Meets | 2015-12-31 | -1193 | 40%
Facilities Services | VoIP Upgrade (Phase 2 Hardware Replacement) | J. Lusardi | Major | Target | Meets | 2015-09-30 | -1285 | 30%
Facilities Services | Wireless Device Cost Analysis | W. Moran | Major | Target | Meets | 2015-12-31 | -1193 | 30%
OMWI | Employee Training Module | M. Noonan | Major | Target | Meets | 2015-11-30 | -1224 | 60%
OMWI | Enhance Vendor Outreach | M. Noonan | Major | Target | Meets | 2015-09-30 | -1285 | 60%
OMWI | Vendor Database System | M. Noonan | Major | Target | Meets | 2015-10-31 | -1254 | 60%
Project Goals On Track for…
[10 empty] | Meets | Exceeds | Outstanding
[9 empty] | Human Resources | 6 | 0 | 0
[9 empty] | Facilities Services | 3 | 0 | 0
[9 empty] | OMWI | 3 | 0 | 0
[9 empty] | Corporate Services | 0 | 0 | 0
[9 empty] | Total | 12 | 0 | 0
Project Breakdown by Team & Project
[10 empty] | Major | Project | Special | Total
[9 empty] | Human Resources | 6 | 0 | 0 | 6
[9 empty] | Facilities Services | 3 | 0 | 0 | 3
[9 empty] | OMWI | 3 | 0 | 0 | 3
[9 empty] | Corporate Services | 0 | 0 | 0 | 0
[9 empty] | Total | 12 | 0 | 0 | 12
Formulas:
Days Left = [Target Date]-(TODAY())

## Projects
Corporate Services
2015 PROJECTS
Overview
Team | Project | Project Manager | Project Type | Progress | Proposed Rating | Target Date | Days Left | % Complete | Dashboard
Human Resources | Human Resources Technology Goal | V. Kang / K. Mitchell | Project | Target | Meets | 2015-12-31 | -1193 | 30%
Human Resources | Officer Physicals | M. Sanders | Project | Complete | Outstanding | 2015-09-30 | -1285 | 100%
Facilities Services | JC Renovations | E. Gonzalez | Project | Target | Meets | 2015-09-30 | -1285 | 80%
Facilities Services | JC UPS/Generator Tie-In & NY UPS Return | J. Pask | Project | Target | Meets | 2015-10-30 | -1255 | 20%
Facilities Services | NY Copier Lease Renewals | J. Pask | Project | Target | Meets | 2015-09-30 | -1285 | 10%
Facilities Services | Pitney Bowes Mail Machine Replacement | J. Pask | Project | Complete | Exceeds | 2015-04-30 | -1438 | 100%
Facilities Services | FHFA Examiners visit | T. Ford | Project | Complete | Meets | 2015-05-15 | -1423 | 100%
Facilities Services | Logo Redesign | J. Pask | Project | Complete | Meets | 2015-05-30 | -1408 | 100%
Facilities Services | JC Space Refresh | W. Williams | Project | Target | Meets | 2015-10-30 | -1255 | 50%
Facilities Services | Lawson Training (RQC and SME) | J. Pask | Project | Behind | Meets | 2015-12-31 | -1193 | 20%
Facilities Services | Lawson PO & RQL Future | J. Lusardi | Project | Target | Meets | 2015-10-31 | -1254 | 20%
OMWI | OMWI 2014 Status Report | M. Noonan | Project | Complete | Meets | 2015-02-28 | -1499 | 100%
OMWI | Future Planning for OMWI Initiatives | M. Noonan | Project | Target | Meets | 2015-12-31 | -1193 | 40% | Project Goals On Track for…
Corporate Services | Project Management Program | M. Noonan | Project | Complete | Meets | 2015-06-30 | -1377 | 100% |  | Meets | Exceeds | Outstanding
[9 empty] | Human Resources | 1 | 0 | 1
[9 empty] | Facilities Services | 8 | 1 | 0
[9 empty] | OMWI | 2 | 0 | 0
[9 empty] | Corporate Services | 1 | 0 | 0
[9 empty] | Total | 12 | 1 | 1
Project Breakdown by Team & Project
[10 empty] | Major | Project | Special | Total
[9 empty] | Human Resources | 0 | 2 | 0 | 2
[9 empty] | Facilities Services | 0 | 9 | 0 | 9
[9 empty] | OMWI | 0 | 2 | 0 | 2
[9 empty] | Corporate Services | 0 | 1 | 0 | 1
[9 empty] | Total | 0 | 14 | 0 | 14
Formulas:
Days Left = [Target Date]-(TODAY())

## Special Projects
Corporate Services
2015 SPECIAL PROJECTS
Overview
Team | Project | Project Manager | Project Type | Progress | Proposed Rating | Target Date | Days Left | % Complete
Human Resources | TBD | TBD | Special
Facilities Services | TBD | TBD | Special
Dashboard
Project Goals On Track for…
[10 empty] | Meets | Exceeds | Outstanding
[9 empty] | Human Resources | 0 | 0 | 0
[9 empty] | Facilities Services | 0 | 0 | 0
[9 empty] | OMWI | 0 | 0 | 0
[9 empty] | Corporate Services | 0 | 0 | 0
[9 empty] | Total | 0 | 0 | 0
Project Breakdown by Team & Project
[10 empty] | Major | Project | Special | Total
[9 empty] | Human Resources | 0 | 0 | 1 | 1
[9 empty] | Facilities Services | 0 | 0 | 1 | 1
[9 empty] | OMWI | 0 | 0 | 0 | 0
[9 empty] | Corporate Services | 0 | 0 | 0 | 0
[9 empty] | Total | 0 | 0 | 2 | 2

## All Projects
Corporate Services
2015 ALL PROJECTS
Overview
Team | Project | Project Manager | Project Type | Progress | Proposed Rating | Target Date | Days Left | % Complete | Dashboard
Human Resources | Project Team Goals | M. Tse-Gonzalez | Major | Target | Meets | 2015-10-31 | -1254 | 30%
Human Resources | Career Pathing | N. Rivera-Mendez | Major | Target | Meets | 2015-10-31 | -1254 | 60%
Human Resources | Officer Criteria | M. Tse-Gonzalez | Major | Target | Meets | 2015-10-31 | -1254 | 10%
Human Resources | Recognition Award Program | N. Rivera-Mendez | Major | Target | Meets | 2015-10-31 | -1254 | 50%
Human Resources | Continuing Professional Education | N. Rivera-Mendez | Major | Target | Meets | 2015-10-31 | -1254 | 40%
Human Resources | Employee Wellness | M. Sanders | Major | Target | Meets | 2016-01-01 | -1192 | 0%
Facilities Services | Real Estate Program | E. Gonzalez | Major | Target | Meets | 2015-12-31 | -1193 | 40%
Facilities Services | VoIP Upgrade (Phase 2 Hardware Replacement) | J. Lusardi | Major | Target | Meets | 2015-09-30 | -1285 | 30%
Facilities Services | Wireless Device Cost Analysis | W. Moran | Major | Target | Meets | 2015-12-31 | -1193 | 30%
OMWI | Employee Training Module | M. Noonan | Major | Target | Meets | 2015-11-30 | -1224 | 60%
OMWI | Enhance Vendor Outreach | M. Noonan | Major | Target | Meets | 2015-09-30 | -1285 | 60%
OMWI | Vendor Database System | M. Noonan | Major | Target | Meets | 2015-10-31 | -1254 | 60%
Human Resources | Human Resources Technology Goal | V. Kang / K. Mitchell | Project | Target | Meets | 2015-12-31 | -1193 | 30%
Human Resources | Officer Physicals | M. Sanders | Project | Complete | Outstanding | 2015-09-30 | -1285 | 100%
Facilities Services | JC Renovations | E. Gonzalez | Project | Target | Meets | 2015-09-30 | -1285 | 80%
Facilities Services | JC UPS/Generator Tie-In & NY UPS Return | J. Pask | Project | Target | Meets | 2015-10-30 | -1255 | 20%
Facilities Services | NY Copier Lease Renewals | J. Pask | Project | Target | Meets | 2015-09-30 | -1285 | 10%
Facilities Services | Pitney Bowes Mail Machine Replacement | J. Pask | Project | Complete | Exceeds | 2015-04-30 | -1438 | 100%
Facilities Services | FHFA Examiners visit | T. Ford | Project | Complete | Meets | 2015-05-15 | -1423 | 100%
Facilities Services | Logo Redesign | J. Pask | Project | Complete | Meets | 2015-05-30 | -1408 | 100%
Facilities Services | JC Space Refresh | W. Williams | Project | Target | Meets | 2015-10-30 | -1255 | 50%
Facilities Services | Lawson Training (RQC and SME) | J. Pask | Project | Behind | Meets | 2015-12-31 | -1193 | 20%
Facilities Services | Lawson PO & RQL Future | J. Lusardi | Project | Target | Meets | 2015-10-31 | -1254 | 20%
OMWI | OMWI 2014 Status Report | M. Noonan | Project | Complete | Meets | 2015-02-28 | -1499 | 100% | Project Goals On Track for…
OMWI | Future Planning for OMWI Initiatives | M. Noonan | Project | Target | Meets | 2015-12-31 | -1193 | 40% |  | Meets | Exceeds | Outstanding
Corporate Services | Project Management Program | M. Noonan | Project | Complete | Meets | 2015-06-30 | -1377 | 100% | Human Resources | 7 | 0 | 1
[9 empty] | Facilities Services | 11 | 1 | 0
Human Resources | TBD | TBD | Special | TBD |  |  |  |  | OMWI | 5 | 0 | 0
Facilities Services | TBD | TBD | Special | TBD |  |  |  |  | Corporate Services | 1 | 0 | 0
[9 empty] | Total | 24 | 1 | 1
Project Breakdown by Team & Project
[10 empty] | Major | Project | Special | Total
[9 empty] | Human Resources | 6 | 2 | 1 | 9
[9 empty] | Facilities Services | 3 | 9 | 1 | 13
[9 empty] | OMWI | 3 | 2 | 0 | 5
[9 empty] | Corporate Services | 0 | 1 | 0 | 1
[9 empty] | Total | 12 | 14 | 2 | 28
Formulas:
Days Left = [Target Date]-(TODAY())

## HR-Project Team Goals
Human Resources
Major Project
HR Project Team Goals
Ground Level View
Project Progress: | Target
Project Status as of: | 2015-06-08
% Complete: | 30%
Target Date: | 2015-10-31
Proposed Rating: | Meets
Project Manager: | Noemi Rivera-Mendez |  | Project Summary:
Team Members:
|  |  | Project Budget: | 0
|  |  | Days Left: | 145
Current Status:
Mercer met with HR, MC members and the CEO individually to gain their insight regarding Bankwide Project Team Goals
Next Steps:
Mercer provided a report with their recommendations at the June 2nd MC meeting. Next MC meeting for further discussion, the week of June 15.
Current Concern/Problem:
N/A
Potential Resolution:
I plan to…
Task Name | Resources | Duration | Start | Finish | % Work Complete
Mercer submits SOW-Contract approval | Noemi |  | 2015-03-05 | 3/20/2015/ | 95%
Conduct a project planning meeting with Human Resources to confirm project approach, work steps, deliverables, Mercer/FHLB roles and responsibilities and timing | Mercer |  | 2015-03-18 | 2015-03-18 | 100%
Conduct individual interviews with Group Heads | Mercer |  | 2015-03-24 | 2015-04-08 | 100%
Prepare draft of recommendation and present to HR | Mercer |  | 2015-04-17 |  | 100%
Review draft provide feedback- Mercer revises if necessary | Noemi/Mildred/ Edwin |  | 2015-04-21 | 2015-05-28 | 100%
Present to Management Committee | Mercer |  | 2015-06-02 | 2015-06-02 | 100%
Modify recommendations if necessary | Mercer
Present to Management Committee for approval | Mildred/Mercer |  | 2015-06-11
Implement changes |  |  | 2015-09-01
Modify procedures: | Noemi
Goal 1 - Meets Requirements
Goal 2 - Exceeds Requirements
Goal 3 - Outstanding
Bi-Weekly Update History
Identify ways to enhance goal measures, team membership, project ratings and alternative reward concepts pertaining to use of lump sum awards to help ensure consistency across.

## HR-Career Pathing
Human Resources
Major Project
Career Pathing
Ground Level View
Project Progress: | Target
Project Status as of: | 2015-07-01
% Complete: | 60%
Target Date: | 2015-10-31
Proposed Rating: | Meets
Project Manager: | Noemi Rivera-Mendez |  | Project Summary:
Team Members:
|  |  | Project Budget: | 0
|  |  | Days Left: | 122
Current Status:
PMO group (Sean Borde) his template is almost complete. Sean was out for 2 weeks his team has not progressed. I met with Sean on 6/23 he was going to follow up with his team. We are scheduled to meet on 7/3 and 7/13 at which point a final draft is expected. Custody and Pledging we one last time with Mercer on 6/16 to cover loose ends and questions. Mercer provided their final draft to Bank on 6/30. I am scheduled to meet with Mike to wrap up any loose ends and finalize the template.
Next Steps:
Review the final draft submitted by Mercer to Custody and Pledging. And provide Sean and his team additional assistance to complete their career pathing structure.
Current Concern/Problem:
None
Potential Resolution:
Not applicable
Task Name | Resources | Duration | Start | Finish | % Work Complete
PMO Group
Review key documents(pd's and org charts) to develop a detailed understanding of job family dept structure, position roles and responsibilities | Noemi |  | 2015-03-23 | 2015-04-03 | 100%
Conduct a project planning meeting with Sean Borde to confirm project approach, work steps, deliverables, roles and responsibilities and timing | Noemi |  | 2015-04-09 | 2015-04-09 | 100%
Prepare draft Career path template for PMO with appropriate active positions and provide recommendations for career path positions | Noemi |  | 2015-04-10 | 2015-04-23 | 100%
Submit draft to Sean | Noemi |  | 2015-04-24 | 2015-04-24 | 100%
Meet with Sean and Team as necessary to answer questions | Noemi |  | 5/15/2015 6/15/2015 |  | 50%
Areas to be completed by Sean's team
Specific experience Broadening experience Feeder roles Next roles | Sean, Kelvin,Erika |  | 2015-04-24 |  | 30%
Review draft career path submitted by PMO team and enhance,edit, modify as necessary from discussions | Noemi, PMO team |  | 2015-06-18
Develop a competency model showing level of competencies required for successful performance of each role | Noemi/Sean |  | 2015-06-25
Member Services- Custody Pledeging
Meet with Paul Heroux to determine which group in MS would start with the Career Path Pilot | Noemi |  | 2015-03-10 | 2015-03-10 | 100%
Meet with Mike Volpe to provide overview of process with Mercer | Noemi |  | 2015-04-14 |  | 100%
Follow up with Mercer and Mike to provide insight | Noemi |  | continuous |  | 50%
Conduct a project planning meeting with Human Resources to confirm project approach, work steps, deliverables, Mercer/FHLB roles and responsibilities and timing | Noemi/Mercer |  | 2015-04-21 |  | 100%
Provide Mercer with key documents to develop their understanding of the job family such as-position descriptions and Org Charts | Noemi |  | 2015-04-20 |  | 100%
Review key documents to develop a detailed understanding of job family organizational structure, position roles and responsibilities and any work that has been done to date to describe career paths and competencies | Mercer |  | 2015-04-20 | 2015-05-13 | 80%
Conduct a group orientation meeting with the Head of Member Services and his direct reports to describe project objectives, methodology, career path components, career path design process and their role | Noemi/Mercer |  | 2015-04-20 | 2015-04-20 | 100%
Conduct 1 hour, individual interview with 1 Director to get input on key career path components | Mercer |  | 2015-04-20 | 2015-04-20 | 100%
Prepare draft career path for Member Services based on Mercer consulting experience and FHLB’s input. Career path components include the following for each role: | Mercer |  | 2015-05-11 |  | 50%
– Major responsibilities --Feeder roles, where talent comes from within and outside FHLB --Next moves, opportunities for employees to progess within specific job family and across the organization Job family specific and broadening experiences required to be successful in current role for career progression Competency skills area
Review draft career path with Human Resources and Member Services | Mercer |  | 2015-05-13 | 2015-05-13
Provide second draft to Human Resources | Mercer |  | 2015-06-15
Review changes made after the last meeting and implement any changes not captured | All |  | 2015-06-16 |  | 100%
Provide final version of the career path to HR | Mercer |  | 2015-06-30 |  | 100%
Do final review of Mercer's submission- meet with Mike V to ensure all requests are captured and potential future career paths are captured as well | Noemi |  | 2015-07-14
Goal 3 - Outstanding
Bi-Weekly Update History | 2015-05-22
Current Status:
I have met twice with PMO group (Sean Borde) his template is almost complete. They are scheduled to submit their first draft template to me on June 15 for my review. With Custody and Pledging we have had two meetings with Mercer and we are scheduled for another on June 16 to get a draft of the template they completed for this team.
Next Steps:
Review the template completed by PMO and Mercer and provide feedback
Current Concern/Problem:
None
Potential Resolution:
Not applicable
Develop Career Path Architecture for second job family within Enterprise Services and one job family within Member Services

## HR-Officer Criteria
Human Resources
Major Project
Officer Criteria
Ground Level View
Project Progress: | Target
Project Status as of: | 2015-05-15
% Complete: | 10%
Target Date: | 2015-10-31
Proposed Rating: | Meets
Project Manager: | Mildred Tse-Gonzalez |  | Project Summary:
Team Members: | Edwin Artuz
Noemi Rivera-Mendez
Virginia Kang
|  |  | Project Budget: | 0
|  |  | Days Left: | 169
Current Status:
Mercer met with HR, MC members and the CEO individually to gain their insight regarding Officer criteria.
Next Steps:
Mercer will report their recommendations at the June 2nd MC meeting.
Current Concern/Problem:
Potential Resolution:
Task Name | Resources | Duration | Start | Finish | % Work Complete
Mercer submits SOW-Contract approval | Noemi |  | 2015-03-05 | 3/20/2015/ | 95%
Conduct a project planning meeting with Human Resources to confirm project approach, work steps, deliverables, Mercer/FHLB roles and responsibilities and timing | Mercer |  | 2015-03-18 | 2015-03-18 | 100%
Conduct individual interviews with Group Heads | Mercer |  | 2015-03-24 | 2015-04-08 | 100%
Prepare draft of recommendation and present to HR | Mercer |  | 2015-04-17 |  | 100%
Review draft provide feedback- Mercer revises if necessary | Noemi/Mildred/ Edwin |  | 2015-04-21 | 2015-05-28 | 100%
Present to Management Committee | Mercer |  | 2015-06-02 | 2015-06-02 | 100%
Modify recommendations if necessary | Mercer
Present to Management Committee for approval | Mildred/Mercer |  | 2015-06-11
Implement changes |  |  | 2015-09-01
Modify procedures:
Goal 1 - Meets Requirements
Goal 2 - Exceeds Requirements
Goal 3 - Outstanding
Bi-Weekly Update History
Enhance the current top-down (33% of the approved budgeted employee headcount) and individual officer criteria to better define career paths and incentive compensation reward opportunities for employees who are technical specialist or in people manager roles.

## HR-Recognition Award Program
Human Resources
Major Project
Recognition Award Program
Ground Level View
Project Progress: | Target
Project Status as of: | 2015-07-01
% Complete: | 50%
Target Date: | 2015-10-31
Proposed Rating: | Meets
Project Manager: | Noemi Rivera-Mendez |  | Project Summary:
Team Members: | Mildred
Edwin
|  |  | Project Budget: | 88000 | part of overall Mercer cost
|  |  | Days Left: | 122
Current Status:
Spot award increment to $1000 was approved. Recognition award program in discussion. Follow up with MC to follow
Next Steps:
MC group is to meet again in July to review recommendations for Recognition award and make a decision.
Current Concern/Problem:
Recognition award program may be eliminated and a budget provided to managers for end of the year recognition of employee contributions
Potential Resolution:
the recommendation needs to be vetted out by MC group and CFO for budgeting reasons
Task Name | Resources | Duration | Start | Finish | % Work Complete
Mercer submits SOW-Contract approval | Noemi |  | 2015-03-05 | 3/20/2015/ | 95%
Conduct a project planning meeting with Human Resources to confirm project approach, work steps, deliverables, Mercer/FHLB roles and responsibilities and timing | Mercer |  | 2015-03-18 | 2015-03-18 | 100%
Conduct individual interviews with Group Heads | Mercer |  | 2015-03-24 | 2015-04-08 | 100%
Prepare draft of recommendation and present to HR | Mercer |  | 2015-04-17 |  | 100%
Review draft provide feedback- Mercer revises if necessary | Noemi/Mildred/ Edwin |  | 2015-04-21 | 2015-05-28 | 100%
Present to Management Committee | Mercer |  | 2015-06-02 | 2015-06-02 | 100%
Meet with MC members to understand concerns | Edwin - Mildred |  | 2015-06-15 |  | 100%
Spot award recommendations were approved-Recognition award in discussions | Edwin |  | 2015-06-19
Review Recognition Award again with Management Committee | Edwin |  | July
Impement changes
Modify procedures: | Noemi |  | 2015-06-12 | 2015-06-15
Submit procedures to DM for publication | Noemi |  | 2015-06-16 | 2015-06-16
Modify checklists | Noemi |  | 2015-06-18
Communicate to employees | Noemi |  | 2015-06-19
Bi-Weekly Update History | 2015-05-22
Current Status:
This is part of Mercer's over arching project objective. Mercer has met with the Group Heads and received feedback with regards to the award program. Recommendations have been made by Mercer based on feedback to the MC group
Next Steps:
MC group is to meet again on 6/11 along with Mercer and HR team to review recommendations and make a decision.
Current Concern/Problem:
With regards to the Recognition program there does not appear to be a concern
Potential Resolution:
Not applicable
Evaluate the Bank’s current Recognition Award Program (“Program”) that includes Spot and Recognition awards and propose a comprehensive Program that includes additional tools for managers to reward employees for extra effort beyond their current position responsibilities.

## HR-Continuing Prof Education
Human Resources
Major Project
Continuing Professional Education
Ground Level View
Project Progress: | Target
Project Status as of: | 2015-07-02
% Complete: | 40%
Target Date: | 2015-10-31
Proposed Rating: | Meets
Project Manager: | Noemi Rivera-Mendez |  | Project Summary:
Team Members:
|  |  | Project Budget: | 0
|  |  | Days Left: | 121
Current Status:
Received copies of two other FHLB's standards. Utilized MR report to determine who is going for CPE credits (certifications). Draft summary of recommendations was put together
Next Steps:
Meet with specific group heads to determine which certifications are required, which are nice to have, create analysis, proposal and recommended standards together
Current Concern/Problem:
Potential Resolution:
Task Name | Resources | Duration | Start | Finish | % Work Complete
Receive requests submitted to MR via budgeted dollars | Noemi |  | 2015-04-22 |  | 100%
Review data received | Noemi |  | 2015-06-08 |  | 100%
Compartmentalize the data recd- pull only CPE's |  |  |  |  | 100%
Review best practices in the market | Noemi |  | 2015-06-08 |  | 75%
Request current practices from HLB's | Noemi |  | 2015-06-08 |  | 100%
Compile data received from HLB's/and best practices | Noemi |  | 2015-07-14 |  | 50%
Meet with Group Heads to understand which Certifications are required and which are nice to have | Noemi |  | 2015-07-14
Analyze data required vs nice to have | Noemi |  | 2015-07-16
Compose first draft of proposed guidelines | Noemi |  | 2015-07-20
Review with Director HR/Head of Corp Svcs | Noemi |  | 2015-07-22
Meet with Group Heads to gauge concerns | Noemi
Modify as necessary | Noemi
Submit final draft to Director HR/Head of Corp/group heads | Noemi |  | 2015-07-27
Goal 1 - Meets Requirements
Goal 2 - Exceeds Requirements
Goal 3 - Outstanding
Bi-Weekly Update History | 2015-05-22
Current Status:
Received internal data from Management Reporting with regards to proposed budgeted dollars for 2015 for this purpose
Next Steps:
Review data received from MR. Review best practices in the market and other HLB's
Develop a standard for ensuring that Bank paid Continuing Professional Education ("CPE") courses requested by employee are 1)in alignment with the Banks business needs and 2) help manage related expensed

## HR-Employee Wellness
Human Resources
Major Project
Employee Wellness
Ground Level View
Project Progress: | Target
Project Status as of: | 2015-06-30
% Complete: | 0%
Target Date: | 2016-01-01
Proposed Rating: | Meets
Project Manager: | Maelean Sanders |  | Project Summary:
Team Members: | Edwin Artuz
Mildred Tse-Gonzalez
|  |  | Project Budget: | 0
|  |  | Days Left: | 185
Current Status:
Ongoing: Wellness Program Proposal submitted for review and approval. Survey questionnaire in draft mode. Coordinated HSA incentive options for 2016 with Cigna - also included in the draft proposal.
Next Steps:
Approval of wellness proposal and draft of wellness questionnaire for review.
Current Concern/Problem:
N/A
Potential Resolution:
Task Name | Resources | Duration | Start | Finish | % Work Complete
Phase 1- Wellness Proposal
Submit Wellness Proposal for approval | N/A |  | 2015-04-01 | 2015-06-30 | 100%
Submit Calendar of Wellness Events | N/A |  | 2015-04-01 | 2015-11-30 | 100%
Confirm approval of Wellness Proposal | E. Artuz/M. Tse-Gonzalez |  | 2015-07-01 | 2015-07-31 | 0%
Phase 2 - Bank-wide Wellness Survey
Construct questions for survey | HR |  | 2015-07-01 | 2015-07-31 | 15%
Confirm approval of Wellness survey questionnaire | E. Artuz/M. Tse-Gonzalez |  | 2015-08-01 | 2015-08-15 | 0%
Submit Wellness survey into SurveyGizmo | M.Sanders |  | 2015-08-18 | 2015-08-31 | 0%
Distribute survey | M.Sanders |  | 2015-09-01 | 2015-09-15 | 0%
Evaluate responses internally | E. Artuz/M. Tse-Gonzalez |  | 2015-09-17 | 2015-09-30 | 0%
Distribute survey summary to employees | M.Sanders |  | 2015-10-01 | 2015-10-04 | 0%
Phase 3 - Implementation of Employee Wellness Committee
Identify potential committee volunteers via wellness survey | M.Sanders/E. Artuz/M. Tse-Gonzalez |  | 2015-09-07 | 2015-09-11 | 0%
Select potential committee members and notify participants | M.Sanders |  |  |  | 0%
Construct a Wellness charter | M.Sanders/E. Artuz/M. Tse-Gonzalez |  | 2015-11-01 | 2015-12-31 | 0%
Phase 4 - Wellness Incentive HSA Funding
Submit budget for HSA employer contributions for wellness | M.Sanders |  | 2015-08-15 | 2015-09-15 | 0%
Coordinate reimbursement schedule of HSA employer dollars with Payroll | Payroll/Benefits |  | 2015-12-01 | 2015-12-31 | 0%
Announce Wellness incentive program to employees | M.Sanders |  | 2015-12-01 | 2015-12-31 | 0%
Phase 5 - Coordinate Biometric Screenings and On-site Wellness Seminars
Coordinate on-site biometric screening vendor with Cigna | M.Sanders/Cigna |  | 2016-01-01 | 2016-02-28 | 0%
Reserve conference rooms for screenings | M.Sanders |  | 2016-03-01 | 2016-03-07 | 0%
Goal 1 - Meets Requirements
Identify EE and Dependent High Risk Factors
Compose Comprehensive Wellness Program for Implementation
Prepare and distribute communication to employees in time for Open Enrollment
Goal 2 - Exceeds Requirements
Create a Wellness Committee of Employees
Develop Calendar of events for 2016
Resolution of Major Obstacles or Issues
Goal 3 - Outstanding
Bi-Weekly Update History
Current Status:
This project is currently underway. Gathering materials from potential wellness vendors and reviewing 2014 medical experience reports to determine health factors within the Bank.
Next Steps:
To draft a Wellness Proposal for the 2016 Plan year.
Current Concern/Problem:
Ensuring our wellness initiatives are in line with ACA requirements.
Potential Resolution:
Involve Legal throughout each step of the wellness initiative project.
To provide market aligned employee wellness programs to enable employees to make informed decisions in their on-going health & welfare and to help the Bank manage expenses.

## FS-Real Estate Program
Facilities Services
Major Project
Real Estate Program (Workplace Strategy)
Ground Level View
Project Progress: | Target
Project Status as of: | 2015-07-01
% Complete: | 40%
Target Date: | 2015-12-31
Proposed Rating: | Meets
Project Manager: | Eric Gonzalez |  | Project Summary:
Team Members:
Walter Moran
Edwin Artuz
Joe Lusardi |  |  | Project Budget: | 110000
Mark Noonan |  |  | Days Left: | 183
Current Status:
The project team met with the Spector Group and Provided the MC Presentation, Steelcase visits, Site Visits, GH Interviews, Surveys
Next Steps:
Continue with Spector, Obtain Egineer and PM
Current Concern/Problem:
Completing the RFP prior to September and updates to MC presentation
Potential Resolution:
Work with Team members to push the RFP and Interview sessions
Task Name | Resources | Duration | Start | Finish | % Work Complete
Project Initiation |  |  | 2015-01-01 | 2015-02-27 | 100%
Project Charter |  |  |  | 2015-02-23 | 100%
Project Goal |  |  |  | 2015-02-23 | 100%
Phase 1: Engage Consultant |  |  |  |  | 100%
Requirements Definition |  |  |  |  | 100%
RFP's |  |  |  |  | 100%
Vendor Scoring Matrix |  |  |  |  | 100%
Contract Execution |  |  |  |  | 100%
Phase II: Planning |  |  |  |  | 100%
Schedule |  |  |  |  | 100%
MC Education Session |  |  |  |  | 100%
Steelcase Visits |  |  |  |  | 100%
Site Visits |  |  |  |  | 100%
MC Schedule Review |  |  |  |  | 100%
CBRE Kickoff meeting |  |  |  |  | 100%
Phase III: Diagnostic and Data Gathering
E-Survey |  |  |  |  | 100%
Group Head Interviews |  |  |  |  | 100%
Observations |  |  |  |  | 100%
Vender Evaluation |  |  |  |  | 0%
Space Programming Report |  |  |  |  | 25%
Presentation to MC |  |  |  |  | 0%
Phase IV: Future State Planning Phase
Engineer RFP |  |  |  |  | 15%
Architectural RFP |  |  |  |  | 5%
Project Manager RFP |  |  |  |  | 5%
Current State Assessment Report |  |  |  |  | 5%
Space Requirements Report
MC Update
Phase V: Recommendation Phase
MC Presentation of Results
MC Signoffs on Space Requirements
Goal 1 - Meets Requirements
Phase 1: Engage Consultant |  |  | 2015-01-01 | 2015-03-31
Phase II: Planning |  |  | 2015-04-01 | 2015-04-30
Phase III: Diagnostic and Data Gathering |  |  | 2015-05-01 | 2015-08-30
Goal 2 - Exceeds Requirements
Phase IV: Future State Planning Phase |  |  | 2015-09-01 | 2015-10-31
Goal 3 - Outstanding
Phase V: Recommendation Phase |  |  | 2015-11-01 | 2015-12-31
Bi-Weekly Update History
Develop real estate and space occupancy options for the New York and New Jersey offices that align with the Bank’s long term strategic and operational objectives.

## FS-VoIP Upgrade
Facilities Services
Major Project
VoIP Upgrade
Ground Level View
Project Progress: | Target
Project Status as of: | 2015-06-30
% Complete: | 30%
Target Date: | 2015-09-30
Proposed Rating: | Meets
Project Manager: | Joseph Lusardi |  | Project Summary:
Team Members:
Jon Pask
Eric Gonzalez
|  |  | Project Budget: | 181000
|  |  | Days Left: | 92
Current Status:
On-Track
Next Steps:
1)NY build-out on 7/17
2)Coordinate NY build-out
3) Secure support agreement annual agreement
Current Concern/Problem:
A) Security concerns from Info Security
B) 1X Mobile/CES Handset Server support
Potential Resolution:
a)Work with ISO to complete Security Plan requirements(in progress)
b) Work with Nick & Rodger for Bank to support server (in progress)
Task Name | Resources | Duration | Start | Finish | % Work Complete
Phase-1 Target Date: June 2015
Project Charter |  |  | 2015-01-01 | 2015-02-28 | 100%
S8800 Hardware Replacement BID Analysis |  |  | 2015-01-01 | 2015-03-31 | 100%
Architectural Redesign Diagram |  |  | 2015-01-01 | 2015-04-30 | 100%
Complete server build-out/installation of VoIP CM’s servers at JC |  |  | 2015-06-01 | 2015-06-30 | 100%
Relocation of ESS’s to Sterling Virginia DR colo-site |  |  | 2015-06-01 | 2015-06-30
Phase- 2 Target Date: July 2015
Complete server build-out/installation of VoIP CM’s servers at VA
Complete server build-out/installation of VoIP CM’s servers at NY |  |  | 2015-07-01 | 2015-07-31
Testing of ancillary server capabilities |  |  | 2015-07-01 | 2015-07-31
Testing and Training of Aura Voice Mail Messaging |  |  | 2015-07-01 | 2015-07-31
Maintenance Agreement Renewals |  |  | 2015-07-01 | 2015-07-31
Phase-3 Target Date: September 2015 |  |  | 2015-08-01 | 2015-09-30
Project Closure Documents |  |  | 2015-08-01 | 2015-09-30
Annual DR Telecommunications Test |  |  | 2015-08-01 | 2015-09-30
Research of any new features and rollout to test group |  |  | 2015-08-01 | 2015-09-30
Goal 1 - Meets Requirements
Meets requirements will be achieved if phase-1 is completed by the target date.
Goal 2 - Exceeds Requirements
Exceeds requirements will be achieved if phase 1 and 2 are both completed by the target date.
Goal 3 - Outstanding
Outstanding will be achieved if phase 1, 2, and 3 are achieved by the specified Target Dates, and the overall project is under budget 10% or more
Current Status:
On-Track
Next Steps:
1)DC2 build-out in VA 6/26
2)Plan NY build-out
3) Secure support agreement one month extension
Current Concern/Problem:
A) Security concerns from Info Security
B) 1X Mobile/CES Handset Server support
Potential Resolution:
a)Work with ISO to complete Security Plan requirements(in progress)
b) Work with Nick & Rodger for Bank to support server
Bi-Weekly Update History
Upgrade the VoIP hardware on key equipment and migrate to a virtual environment.

## FS-Wireless Device Cost Anal
Facilities Services
Major Project
Wireless Device Cost Analysis
Ground Level View
Project Progress: | Target
Project Status as of: | 2015-07-01
% Complete: | 30%
Target Date: | 2015-12-31
Proposed Rating: | Meets
Project Manager: | Walter Moran |  | Project Summary:
Team Members:
|  |  | Project Budget: | 0
|  |  | Days Left: | 183
Current Status:
The current state assessment target date has been moved from July to August. The Future State phase: Identify cost saving opportunities (for iPads) was moved from September to August. This project is on track for completion by the revised due dates.
Next Steps
Identify and implement cost saving opportunities for iPads will be moved up from September/December to August to align cost saving opportunities with the 2016 operating expense planning budget.
Current Concern/Problem:
None
Potential Resolution:
N/A
Task Name | Resources | Duration | Start | Finish | % Work Complete
1) Current State Assessment |  |  |  | 2015-07-30
Identify carrier reports (Verizon and AT&T) to obtain the required data to prepare a *3-year cost analysis. (*subject to carrier availability).
Prepare 3-year cost (trend) analysis that incorporates the following information:
Annual cost of Wireless Device Program
Number of devices (iPhone/iPads)
Employee name, rank, title, type of device issued,etc.
Cost of Wireless Program by cost center (*18 months)
Cost of Wireless Program by division (*18 months)
Business justification
Review current state analysis with Group Heads
Discuss potential cost saving opportunities
2) Future state |  |  |  | 2015-09-30
Develop a Mobile Device Issuance standard in collaboration with Group Heads
Identify cost saving opportunities
3) Implement recommendations |  |  |  | 2015-12-30
Publish Standard
Develop strategies to implement cost saving opportunities in 2016
Goal 1 - Meets Requirements
Meets requirements will be achieved if items 1 and 2 are completed within the required timeframe.Potential issues outside of the project team’s control impacting the target date for completion or project stoppage will be evaluated based on the effort and level of accomplishment by the team.
Goal 2 - Exceeds Requirements
To achieve an Exceeds, in addition to completing the Meets requirement deliverables and timeframes, recommendation(s) for item 3 are implemented and cost savings can be supported and documented.
Goal 3 - Outstanding
Bi-Weekly Update History
Current Status: |  |  |  |  | 2015-06-01
On schedule for July deliverable.
Next Steps:
Review vendor reports and analyze data
Current Concern/Problem:
None
Potential Resolution:
N/A
Facilities Services currently manages the Bank’s Wireless Device Program (iPhone/*iPad). The Facilities Services budget comprises of iPhone hardware and monthly carrier plans for both iPhone and iPads (*Enterprise Services budgets for the iPad hardware). Despite efforts by the Facilities Services Team to manage carrier plans to contain cost, the current expense to support this program has been exponentially increasing. Objectives:
1. Prepare a *3-year (trend) analysis showing the major cost/expense factors of the current Wireless Device Program. *Data for certain components of the analysis may only be available for 12 months.
2. Review current program and collaborate with Group Heads to establish a standard for mobile devices.
3. Identify potential cost savings management strategies in this area while recognizing that mobile communications is an integral part of our business.

## OMWI-Training Module
OMWI
Major Project
OMWI Employee Training Module
Ground Level View
Project Progress: | Target
Project Status as of: | 2015-07-01
% Complete: | 60%
Target Date: | 2015-11-30
Proposed Rating: | Meets
Project Manager: | Mark Noonan |  | Project Summary:
Team Members:
Jessey Abraham
Noemi Rivera-Mendez
|  |  | Project Budget: | 0
|  |  | Days Left: | 152
Current Status:
This project is in the 3rd draft phase. We reached out to the other FHLBs. Des Moines, Indianapolis, Chicago, and Dallas responded.
Next Steps:
To finish the 3rd draft of the OMWI PowerPoint deck.
Current Concern/Problem:
Potential Resolution:
Task Name | Resources | Duration | Start | Finish | % Work Complete
Phase 1- Define & Initiate
Create Project Charter | Mark Noonan | 10 days | 2015-03-01 | 2015-03-10 | 100%
Set up OMWI Employee Training Folder | Mark Noonan | 10 days | 2015-03-01 | 2015-03-10 | 100%
Define team members | Mark Noonan | 10 days | 2015-03-01 | 2015-03-10 | 100%
Send kickoff email explaining the project plan | Mark Noonan, Jessey Abraham, Noemi Rivera-Mendez | 10 days | 2015-03-10 | 2015-03-20 | 100%
Kick-off Meeting to explain initial Plan. | Mark Noonan, Jessey Abraham | 11 days | 2015-03-20 | 2015-03-31 | 100%
Have Compliance send Mark Net Dimension "test trainings" to learn how we do online training | Mark Noonan, Jessey Abraham | 10 days | 2015-04-01 | 2015-04-10 | 100%
Follow up with Net Dimensions after first contact - receive their initial Ideas/Options | Mark Noonan | 3 days | 2015-04-01 | 2015-04-03 | 100%
Put together my own Slides/Ideas for the Training Module | Mark Noonan | 3 days | 2015-04-10 | 2015-04-12 | 75%
Attend ILR Cornell Training Workshop - Best Practices | Mark Noonan | 2 days | 2015-04-12 | 2015-04-13 | 100%
Phase 2 - Planning
Begin to decide how the training will be done: how long will the test be? How many slides? How will it be scored? Should people acknowledge having taken the test? Etc etc | Mark Noonan | 7 days | 2015-04-13 | 2015-04-20 | 75%
Meet with Net Dimensions in person | Mark Noonan | 11 days | 2015-04-20 | 2015-05-01
Test out Net Dimensions options for OMWI Training | Mark Noonan | 15 days | 2015-05-01 | 2015-05-15
Decide if Net Dimensions can be used. If not, seek out another Vendor | Mark Noonan | 15 days | 2015-05-15 | 2015-06-01 | 100%
If Net Dimensions can be used, use their template to create our own Training Module | Mark Noonan | 15 days | 2015-06-01 | 2015-06-15
Test out possible Training Module template with Pilot Group | Mark Noonan, Noemi Rivera-Mendez, Susan Yan | 15 days | 2015-06-15 | 2015-06-30
Reach out to Compliance to see what else they will need in order to launch this Module to employees | Mark Noonan, Jessey Abraham | 15 days | 2015-07-01 | 2015-07-15
Reach out to Team Members for feedback | Mark Noonan, Edwin Artuz, Mildred Tse-Gonzalez, Virginia Kang | 16 days | 2015-07-15 | 2015-07-31
Reach out to Legal for feedback | Mark Noonan, Paul Friend | 10 days | 2015-08-01 | 2015-08-10
Once vetted, create final version to be tested | Mark Noonan | 16 days | 2015-08-15 | 2015-09-01
Test final version on Pilot Group | Mark Noonan, Jessey Abraham, Noemi Rivera-Mendez | 15 days | 2015-09-01 | 2015-09-15
Create Cover Memo for Launch | Mark Noonan | 15 days | 2015-09-15 | 2015-09-30
Get feedback from Pilot Group | Mark Noonan | 15 days | 2015-09-15 | 2015-09-30
Goal 1 - Meets Requirements
Phase 3 - Execute
Launch online Training Tool to all employees. | Mark Noonan | 16 days | 2015-09-15 | 2015-10-01
Goal 1 - Meets Requirements
Launch online Training Tool to all new hires. | Mark Noonan | 30 days | 2015-10-01 | 2015-11-01
Create Process to…
Goal 1 - Meets Requirements
Phase 4 - Monitor & Control
Follow up: check the results of employee's using the Training Module. | Mark Noonan | 15 days | 2015-11-01 | 2015-11-15
Phase 5 - Closing
TBD: plan for future initiatives | Mark Noonan | 16 days | 2015-11-15 | 2015-12-01
Bi-Weekly Update History
Current Status: |  |  |  |  | 2015-06-15
This project is in the 3rd draft phase.
Next Steps:
To finish the 3rd draft of the OMWI PowerPoint deck.
Current Concern/Problem:
How to marry the bank's story with the general D&I story.
Potential Resolution:
Tell a story. And reach out to the other FHLBs to gather any training information they can provide.
To create a new OMWI training module for all employees.

## OMWI-Vendor Outreach
OMWI
Major Project
OMWI Enhance Vendor Outreach
Ground Level View
Project Progress: | Target
Project Status as of: | 2015-07-01
% Complete: | 60%
Target Date: | 2015-09-30
Proposed Rating: | Meets
Project Manager: | Mark Noonan |  | Project Summary:
Team Members:
Joe Lusardi
Jon Pask
|  |  | Project Budget: | 0
|  |  | Days Left: | 91
Current Status:
Two areas of concentration: first, the Purchasing OMWI Plan, and second, identifying 1 OMWI supplier for each bank expiring contract.
Next Steps:
Finalize the purchasing OMWI plan.
Current Concern/Problem:
Potential Resolution:
Task Name | Resources | Duration | Start | Finish | % Work Complete
Phase 1- Define & Initiate
Create Project Charter | Mark Noonan | 10 days | 2015-03-01 | 2015-03-10 | 100%
Setup OMWI Vendor Outreach Folder | Mark Noonan | 10 days | 2015-03-01 | 2015-03-10 | 100%
Define Team Members | Mark Noonan | 10 days | 2015-03-10 | 2015-03-20 | 100%
Compose Kick-off Email to Team | Mark Noonan | 10 days | 2015-03-20 | 2015-03-30 | 100%
Kick-off Meeting to explain initial Plan. (Pushed to April 21 by Joe & Eric because of VoIP priority) | Mark Noonan, Joe Lusardi, Eric Gonzalez | 6 days | 2015-03-25 | 2015-04-01 | 100%
Plan B - Reach out to…Records? (Brian Wiedl), Finance? Who else has access to contracts/agreements? Gain advice from Edwin | Mark Noonan | 3 days | 2015-04-01 | 2015-04-03 | 100%
Phase 2 - Planning
Plan Work Schedule with Joe Lusardi (340 Vendors, 40 OMWI) | Mark Noonan, Joe Lusardi | 5 days | 2015-04-01 | 2015-04-05 | 100%
Reach out to Legal regarding vendors and OMWI vendors. Discuss how to execute with Edwin - gain advice. | Mark Noonan, Joe Lusardi, Paul Friend | 5 days | 2015-04-05 | 2015-04-10 | 100%
Follow up Meeting with Joe - check progress | Mark Noonan, Joe Lusardi | 5 days | 2015-04-10 | 2015-04-15 | 100%
Reach out to Management Reporting regarding coding | Mark Noonan, Shamecca Lazarus | 15 days | 2015-04-15 | 2015-05-01 | 100%
Follow up Meeting with Joe - check progress | Mark Noonan, Joe Lusardi | 15 days | 2015-05-01 | 2015-05-15 | 100%
Follow up Meeting with Joe, Eric Gonzalez - check progress | Mark Noonan, Joe Lusardi, Eric Gonzalez | 15 days | 2015-06-01 | 2015-06-15 | 100%
Phase 3 - Execute
Complete List of Bank Contracts expiring in the next 24 months. | Joe Lusardi, Mark Noonan | 15 days | 2015-04-15 | 2015-05-01 | 100%
Identify at least 1 OMWI Vendor for every expiring Bank contract. Discuss plan with service agreement owners | Joe Lusardi, Mark Noonan | 30 days | 2015-06-01 | 2015-07-01 | 50%
Goal 1 - Meets Requirements
Arrange meeting with service agreement owner and potential OMWI vendor. | Joe Lusardi, Mark Noonan | 30 days | 2015-07-01 | 2015-08-01 | 0%
Set up the process as contracts come due, for an Identified OMWI vendor to be given the opportunity to bid. | Joe Lusardi, Jon Pask, Mark Noonan | 30 days | 2015-08-01 | 2015-09-01 | 0%
Phase 4 - Monitor & Control
Follow up Meeting with Joe, Eric Gonzalez - check progress | Mark Noonan, Joe Lusardi, Eric Gonzalez | 15 days | 2015-07-01 | 2015-07-15 | 0%
Follow up Meeting with Joe, Eric Gonzalez - check progress | Mark Noonan, Joe Lusardi, Eric Gonzalez | 15 days | 2015-08-01 | 2015-08-15 | 0%
Phase 5 - Closing
Goal 1 - Meets Requirements
TBD: plan for future initiatives | Mark Noonan | 15 days | 2015-09-01 | 2015-10-01 | 0%
Bi-Weekly Update History
Current Status: |  |  |  |  | 2015-06-15
This project is on track but dealing with miscommunication.
Next Steps:
Mark and Joe to meet to get their information and plan to move forward on the same path.
Current Concern/Problem:
Getting everyone on the same page.
Potential Resolution:
Meet and develop plan.
To enhance and increase our OMWI vendor bids Bankwide.

## OMWI-Vendor Database System
OMWI
Major Project
Vendor Database System
Ground Level View
Project Progress: | Target
Project Status as of: | 2015-07-01
% Complete: | 60%
Target Date: | 2015-10-31
Proposed Rating: | Meets
Project Manager: | Mark Noonan |  | Project Summary:
Team Members:
Joe Lusardi
Jon Pask
Eric Gonzalez |  |  | Project Budget: | 0
|  |  | Days Left: | 122
Current Status:
This project is on track.
Next Steps:
Received 2 proposals, waiting on the third.
Current Concern/Problem:
CVM's parent company, Altegrity, filed for bankruptcy protection in February. Follow up on the effects of this, if any.
Potential Resolution:
N/A
Task Name | Resources | Duration | Start | Finish | % Work Complete
Phase 1- Define & Initiate
Create Project Charter | Mark Noonan | 10 days | 2015-03-01 | 2015-03-10 | 100%
Setup OMWI Vendor Database System folder | Mark Noonan | 5 days | 2015-03-05 | 2015-03-10 | 100%
Define Team Members | Mark Noonan | 5 days | 2015-03-05 | 2015-03-10 | 100%
Send Kick-off Email to Team | Mark Noonan | 10 days | 2015-03-10 | 2015-03-20 | 100%
Kick-off Meeting to explain initial Plan. (Pushed to April 21 by Joe & Eric because of VoIP priority) | Mark Noonan, Joe Lusardi, Jon Pask, Eric Gonzalez | 7 days | 2015-03-20 | 2015-03-27 | 100%
Phase 2 - Planning
Contact the other FHLBs, find out what services they use (if different than ours) with CVM. And their pricing structure. | Mark Noonan | 7 days | 2015-03-25 | 2015-04-01 | 100%
Contact the other FHLBs, find other viable Vendors (aside from CVM) | Mark Noonan, Joe Lusardi | 15 days | 2015-04-01 | 2015-04-15 | 100%
Research other viable Vendors (aside from CVM). Supplier Gateway, ConnXus, etc | Mark Noonan, Joe Lusardi | 16 days | 2015-04-15 | 2015-05-01 | 100%
Meeting with CVM to discuss new service plan/options to streamline the process. | Mark Noonan, Joe Lusardi | 15 days | 2015-05-01 | 2015-05-15 | 100%
Work with Management Reporting to develop stronger OMWI invoice coding. | Mark Noonan, Joe Lusardi, Claudia Kim | 16 days | 2015-05-15 | 2015-06-01 | 50%
Meet with 2 other Vendors | Mark Noonan, Joe Lusardi | 11 days | 2015-05-20 | 2015-07-01 | 100%
Set up demos with 2 other Vendors | Mark Noonan, Joe Lusardi | 60 days | 2015-06-01 | 2015-08-01 | 100%
Get new bid from CVM | Mark Noonan, Joe Lusardi | 30 days | 2015-08-01 | 2015-09-01 | 50%
Get proposals (bids) from 2 other Vendors | Mark Noonan, Joe Lusardi | 15 days | 2015-08-01 | 2015-09-01 | 50%
Meeting to discuss options | Mark Noonan, Joe Lusardi | 15 days | 2015-09-01 | 2015-09-15
Phase 3 - Execute
Propose a new option with CVM or an alternative with another vendor | Mark Noonan |  | 2015-09-15 | 2015-10-01
Goal 2 - Exceeds Requirements
Phase 4 - Monitor & Control
Review if the new vendor functions are better, worse, or the same as the year prior | Mark Noonan | 30 days | 2015-10-01 | 2015-11-01
Phase 5 - Closing
TBD: plan for future initiatives | Mark Noonan | 15 days | 2015-10-15 | 2015-11-01
Bi-Weekly Update History
Current Status: |  |  |  |  | 2015-06-15
This project is on track.
Next Steps:
To get proposals from the three vendors for the portal and data scrub.
Current Concern/Problem:
N/A
Potential Resolution:
N/A
To review our current vendor (CVM), research possible new vendors, and streamline the scrubbing process.

## HR-Technology Goal
Human Resources
Project
HR Technology Goal
Ground Level View
Project Progress: | Target
Project Status as of: | 2015-06-30
% Complete: | 30%
Target Date: | 2015-12-31
Proposed Rating: | Meets
Project Manager: | Virginia Kang/Khadijah Mitchell |  | Project Summary:
Team Members:
|  |  | Project Budget: | 0
|  |  | Days Left: | 184
Current Status:
Working with PM team to activate Bankwide Goal project for Bank; Vetting one more ATS vendor
Next Steps:
Finalize Bankwide Goals requirements & send to PM team; Continue to work with TMS support on Bankwide goal
Current Concern/Problem:
Potential Resolution:
Task Name | Resources | Duration | Start | Finish | % Work Complete
Goal: Automation – Incentive Compensation Bankwide Goal Process
Build test bank goal plan in TMS | Khadijah |  | 2015-04-28 | 2015-06-26 | 85%
Look at Sharepoint possiblities for Bankwide Goal plan | Khadijah |  | 2015-06-05 | 2015-06-08 | 100%
Reach out to Sharepoint owners to discuss testing | Khadijah |  | 2015-06-05 | 2015-06-10 | 100%
After testing of both Sharepoint & TMS, pick the best solution | Khadijah |  | 2015-08-24 | 2015-08-24 | 0%
Draft implementation timeline for Bankwide Goal plan | Khadijah |  | 2015-08-25 | 2015-08-31 | 0%
Draft communication to goal owners | Khadijah |  | 2015-11-16 | 2015-11-18 | 0%
Inform goal owners of implementation timeline | Khadijah |  | 2015-11-23 | 2015-11-23 | 0%
Testing of goal templates | Khadijah |  | 2015-11-30 | 2015-12-04 | 0%
Final testing of all templates | Khadijah |  | 2015-12-07 | 2015-12-09 | 0%
Email communications | Khadijah |  | 2016-02-01 | 2016-02-01 | 0%
Go live | Khadijah |  | 2016-02-01 | 2016-02-01 | 0%
Update HR Tickler (if applicable) | Khadijah |  |  |  | 0%
Goal: Automation – Incentive Compensation Statements
Speak with TMS to see if it's possible to build a test ICP template | Khadijah |  | 2015-06-05 | 2015-06-05 | 0%
Look at Sharepoint possiblities for ICP Statements | Khadijah |  | 2015-06-05 | 2015-06-08 | 0%
Reach out to Sharepoint owners to discuss testing | Khadijah |  | 2015-06-05 | 2015-06-10 | 0%
After testing of both Sharepoint & TMS, pick the best solution | Khadijah |  | 2015-08-24 | 2015-08-24 | 0%
Draft implementation timeline for ICP Statements | Khadijah |  | 2015-08-25 | 2015-08-31 | 0%
Goal: Recruiting Solution
Establish list of ATS vendors to research | Khadijah |  | 2015-04-03 | 2015-04-10 | 100%
Compile list from recruiting team of requested items | Khadijah |  | 2015-04-09 | 2015-04-10 | 100%
Meet with HR Director to discuss plan | Khadijah |  | 2015-04-17 | 2015-04-17 | 100%
Send RFI to various vendors | Khadijah |  | 2015-04-10 | 2015-04-15 | 100%
Demo various ATS systems | Khadijah |  | 2015-04-14 | 2015-05-19 | 100%
Organize notes from vendor mtgs & demos | Khadijah |  | 2015-05-28 | 2015-07-20 | 30%
Send HR Director notes of each ATS vendor | Khadijah |  | 2015-06-08 | 2015-07-24 | 0%
Based on Director notes & budget, send for RFP | Khadijah |  | 2015-08-03 | 2015-08-17 | 0%
Select ATS vendor | Khadijah |  | 2015-09-14 | 2015-09-18 | 0%
Draft implementation timeline | Khadijah |  | 2015-09-21 | 2015-09-25 | 0%
Goal 1 - Meets Requirements |  |  |  | 2015-12-31
Automate – Incentive Compensation Bankwide Goal Process |  |  |  | 2015-12-31 | 0%
Automate – Incentive Compensation Statements |  |  |  | 2016-01-01 | 0%
Replace current recruiting solution with the objective of enhancing recuiting and selection process and improving metrics |  |  |  | 2016-01-01 | 0%
Goal 1- Exceeds Requirements |  |  |  | 2015-12-31
Implementation of budgeted approved solutions |  |  |  |  | 0%
Identify and create project plan to streamline or automate |  |  | 2015-05-22 | 2015-05-27 | 0%
Write procedures/processes of implemented solutions |  |  |  |  | 0%
Resolution of major obstacles or issues |  |  |  |  | 0%
Bi-Weekly Update History | 2015-06-30
Looking at SharePoint for Bankwide Goals & ICP; Completed demos of ATS vendors
1) address IA 's recommendation to automate Bankwide goals (includes posting Bankwide goal results) & 2) explore products &make recommendations to streamline & automate in various areas within HR.

## HR-Officer Physicals
Human Resources
Project
Officer Physicals
Ground Level View
Project Progress: | Complete
Project Status as of: | 2015-05-27
% Complete: | 100%
Target Date: | 2015-09-30
Proposed Rating: | Outstanding
Project Manager: | Maelean Sanders |  | Project Summary:
Team Members:
|  |  | Project Budget: | 0
|  |  | Days Left: | 126
Current Status:
This project is complete. The EHE International contract has been renewed and executed. Participants were notified of the contract extension through December 31, 2015.
Next Steps:
N/A
Current Concern/Problem:
Potential Resolution:
Task Name | Resources | Duration | Start | Finish | % Work Complete
Notify EHE of Discontinuation of Contract in 2016 |  |  | 2014-11-02 | 2014-12-31 | 100%
Negotiate New Contract with EHE |  |  | 2015-03-01 | 2015-04-30 | 100%
Communicate Termination of EHE relationship to Officer Physical Program Participants in 2016 |  |  | 2015-04-15 | 2015-04-30 | 100%
Draft Plan
Final Plan
Phase 1- Define & Initiate
Phase 2 - Planning
Phase 3 - Execute
Phase 4 - Monitor & Control
Phase 5 - Closing
Goal 1 - Meets Requirements
Goal 2 - Exceeds Requirements
Goal 3 - Outstanding
Bi-Weekly Update History
To renew the Bank's Officer Physical program contract with EHE International through 12/31/2015 before termination of relationship for 2016.

## FS-JC Renovations
Facilities Services
Project
Jersey City Renovations
Ground Level View
Project Progress: | Target
Project Status as of: | 2015-06-01
% Complete: | 80%
Target Date: | 2015-09-30
Proposed Rating: | Meets
Project Manager: | Eric Gonzalez |  | Project Summary:
Team Members:
Jannette Gonzalez
Joe Lusardi
Jon Pask |  |  | Project Budget: | 181136
Tina Ford |  |  | Days Left: | 121
Will Williams
Current Status:
completed office set ups
Completed Dutch door
Next Steps:
Get Electric tied into UPS for Electronic Payments new area
Get badge reader moved for new Electronic payment area
Current Concern/Problem:
Finding Painter at reasonable price
Potential Resolution:
Work with contractor to resolve
Task Name | Resources | Duration | Start | Finish | % Work Complete
1) Carve Out Data Center Hub for Office Operations |  | 8 Weeks from building permit | 2015-03-30 | 2015-05-26 | 100%
2) Build Out of New Training Room and Confr. Room |  | 4 weeks from completion of data center renovation | 2015-05-27 | 2015-06-24 | 100%
3) Coordinate Various Employee Moves |  | 6 weeks if the build out of 3rd floor renovation work. | 2015-05-28 | 2015-07-09 | 90%
4) Relocation of Electronic Payments Room |  |  |  | 2015-09-30 | 15%
5) Close Out All Punch List Items |  |  |  | 2015-09-30 | 90%
Goal 1 - Meets Requirements
Meets requirements will be achieved if items 1, 2 and 3 of the deliverables are completed within the meets required timeframe.
Goal 2 - Exceeds Requirements
Exceeds requirements will be achieved if items 1, 2, 3, 4, and 5 of deliverables are completed within the required timeframe.
Goal 3 - Outstanding
Outstanding will be achieved if all 5 of the deliverables are completed within the meets timeframe and all work and furniture is completed without any out-of-pocket funds from the Bank. This can potentially be accomplished through negotiations with the landlord, third-party vendors, and management of Tenant Improvement and insurance funds.
Bi-Weekly Update History
Work with building management, furniture vendors, and internal stakeholders to renovate the JC Data Hub into useable office space and install 15 new workstations for Bank operations.

## FS-JC UPS-Generator Tie-in
Facilities Services
Project
JC UPS Generator Tie In/NY UPS Return
Ground Level View
Project Progress: | Target
Project Status as of: | 2015-07-01
% Complete: | 20%
Target Date: | 2015-10-30
Proposed Rating: | Meets
Project Manager: | Jon Pask |  | Project Summary:
Team Members:
Will Williams
Eric Gonzalez
Walter Moran
|  |  | Project Budget: | 45000 | 6000
|  |  | Days Left: | 121
Current Status:
Pending Vendor Analysis
Next Steps:
Obtain analysis, Budget approval, and plan for next steps
Current Concern/Problem:
Need to get information from Environectics back quickly to proceed with analysis
Potential Resolution:
Follow up with Environectics
Task Name | Resources | Duration | Start | Finish | % Work Complete
UPS Rental Return |  |  |  | 2015-08-30
Disconnect/Disassemble UPS (NY) |  |  |  | 2015-07-31 | 100%
Package/Pelletize UPS |  |  |  | 2015-07-31
UPS Return Pick Up (Power Super Site)
Get quote from packer | David Aponte |  | 2015-06-09 | 2015-06-09 | 100%
Revise packer quote | David Aponte |  | 2015-06-09 | 2015-06-12 | 100%
Review Logisticts | All |  | 2015-06-11 | 2015-06-11 | 100%
Approve Packer and Electrical work | Jon & David |  | 2015-06-17 | 2015-06-22 | 100%
Schedule Electrical and Packer | Jon & David |  | 2015-06-19 | 2015-06-22 | 50%
Coordinate drop off and pick up with vendors | Jon & David |  | 2015-07-06 | 2015-07-17
Confirm delivery | David Aponte |  | 2015-07-24 | 2015-07-24
Provide closure documentation | Jon |  |  | 2015-08-30
Jersey City Backup Power |  |  |  | 2015-10-30
Legal Review | Barbara |  | 2015-05-04 | 2015-05-04 | 100%
Complete Analysis | Environetics |  | 2015-06-15 | 2015-06-30
Review analysis | All |  | 2015-07-01 | 2015-07-15
Obtain backup power requirements |  |  | 2015-07-16 | 2015-07-24
Develop viable cost effective backup power options |  |  | 2015-07-16 | 2015-07-24
Prepare cost analysis |  |  | 2015-07-16 | 2015-07-24
Discuss with stakeholders |  |  | 2015-07-27 | 2015-07-31
Obtain approval of proposed solution |  |  | 2015-09-08 | 2015-08-15
Negotiate maintenance/Service Level Agreement for UPS backup power infrastructure, if applicable. |  |  | 2015-08-15 | 2015-09-15
Coordinate installation of additional power source, if applicable. |  |  | 2015-09-18 | 2015-10-30
Goal 1 - Meets Requirements
Completion of deliverables by the goal due date. This project has an external dependency: therefore consideration will be given to the overall contribution of the project to meet the project requirements.
Goal 2 - Exceeds Requirements
Consideration will be given to the degree which any of the following are achieved. The Facilities Services Manager will make the recommendation to the Director of Facilities Services.
Bi-Weekly Update History
Evaluate the options for Generator versus UPS tie in, then propose possible solutions and obtain approval to move forward. Post Hurricane Sandy, a 50 KVA rental UPS unit was installed at the NY data center to support the Bank’s production environment. Now that the Production data center has been moved , arrangements need to be made for the return of the rental UPS.

## FS-NY Copier Lease Renewals
Facilities Services
Project
NY Copier Lease Renewals
Ground Level View
Project Progress: | Target
Project Status as of: | 2015-06-30
% Complete: | 10%
Target Date: | 2015-09-30
Proposed Rating: | Meets
Project Manager: | Jon Pask |  | Project Summary:
Team Members:
Tina Ford
Will Williams
Jon Pask |  |  | Project Budget: | 0
Joe Lusardi |  |  | Days Left: | 92
Eric Gonzalez
Current Status:
Started. Received numbers from current vendor and determined it is cheaper to retain current equipment.
Next Steps: Get 2 other proposals
To…
Current Concern/Problem:
The current lease expired on 6/15/15
Potential Resolution:
Continue on a month-to-month until analysis/decision is made
Task Name | Resources | Duration | Start | Finish | % Work Complete
Model Comparison Analysis |  |  |  | 2015-09-30 | 25%
Incumbent Vendor Visit |  |  |  | 2015-06-24 | 100%
Lease VS. Buy Cost Benefit Analysis VS. Extend lease |  |  |  | 2015-09-30 | 25%
Contract Commitment Tracking Form |  |  |  | 2015-09-30
Executed Lease/Maintenance Agreements |  |  |  | 2015-09-30
Training Schedule |  |  |  | 2015-09-30
Goal 1 - Meets Requirements
See Goal, Part of Procurement Program Goals
Goal 2 - Exceeds Requirements
Goal 3 - Outstanding
Bi-Weekly Update History
Vendor Visit on 6/24/15. Preliminaly numbers received.
Prepare a lease analysis and provide options for the NY copiers. Evaluate current usage, health of machines, and propose scenarios for replacement or retention, and lease versus buy analysis.

## FS-Pitney Bowes Mail Replacemen
Facilities Services
Project
Pitney Bowes Mail Machine Replacement
Ground Level View
Project Progress: | Complete
Project Status as of: | 2015-06-01
% Complete: | 100%
Target Date: | 2015-04-30
Proposed Rating: | Exceeds
Project Manager: | Jon Pask |  | Project Summary:
Team Members:
Will Williams
|  |  | Project Budget: | 19000
|  |  | Days Left: | -32
Current Status:
Closed & Completed
Next Steps:
To…
Current Concern/Problem:
The problem is…
Potential Resolution:
I plan to…hit the lottery
Task Name | Resources | Duration | Start | Finish | % Work Complete
Review Current PB contract Due Date |  |  | 2014-12-01 | 2014-12-01 | 100%
Create Analysis |  |  | 2014-12-01 | 2014-12-01 | 100%
Get extension on current Contract |  |  | 2014-12-10 | 2014-12-10 | 100%
Review contract |  |  | 2014-12-31 | 2014-12-31 | 100%
Create CCTF |  |  | 2015-01-01 | 2015-01-01 | 100%
Create Write up justification |  |  | 2015-01-15 | 2015-01-15 | 100%
Order Equipment |  |  | 2015-01-26 | 2015-01-26 | 100%
Take Delivery/Set up and Train |  |  | 2015-02-11 | 2015-02-11 | 100%
Trouble shoot issues |  |  | 2015-02-12 | 2015-02-19 | 100%
Set up final training |  |  | 2015-03-12 | 2015-03-21 | 100%
Get Executed contract back |  |  | 2015-03-12 | 2015-03-31 | 100%
Look into Online backup postage | Will |  | 2015-03-01 | 2015-03-31 | 100%
Close out Documentatio |  |  | 2015-05-15 | 2015-05-18 | 100%
Goal 1 - Meets Requirements
See Goal, Part of Procurement Program Goals
Goal 2 - Exceeds Requirements
Goal 3 - Outstanding
Bi-Weekly Update History
Prepare a lease analysis, and provide options for replacement of the Bank’s New York mail machine. Upon approval, move forward with proposed plan and execute.

## FS-FHFA Examiners Visit
Facilities Services
Project
FHFA Examiners Visit
Ground Level View
Project Progress: | Complete
Project Status as of: | 2015-06-01
% Complete: | 100%
Target Date: | 2015-05-15
Proposed Rating: | Meets
Project Manager: | Tina Ford |  | Project Summary:
Team Members:
Will Williams
Jannette Gonzalez
Allen Jones |  |  | Project Budget: | 0
|  |  | Days Left: | -17
Current Status:
Completed
Next Steps:
Current Concern/Problem:
Potential Resolution:
Task Name | Resources | Duration | Start | Finish | % Work Complete
Coordinate the set up and conversion of conference rooms for use by the examiners. |  |  |  | 2015-03-27 | 100%
Work with IT and Compliance to ensure a smooth ingress and egress transition. |  |  |  |  | 100%
Manage office and conference room space during the examination period to accommodate business needs. |  |  |  | 2015-04-13 | 100%
Prepare office space and seating plan |  |  |  |  | 100%
Provide FS support as needed during examination period |  |  | 2015-04-13 | 2015-05-15 | 100%
Return office space to pre-visit conditions |  |  |  | 2015-05-15 | 100%
Goal 1 - Meets Requirements
All deliverables are completed as required
Goal is completed within the required timeframe and with minimum disruption to Bank operations
Goal 2 - Exceeds Requirements
Additional space planning activities NOT in scope are implemented to provide additional conferencing space to support business operations during the examination visit
Goal 3 - Outstanding
Bi-Weekly Update History
Office preparations for the annual visit of the Federal Housing Finance Agency Examination Team (Safety and Soundness Examination). In preparation for the visit Facilities Services, coordinates a series of activities to facilitate building access, office space requirements and works closely with TSD to provide technology support to the Examination Team.

## FS-Logo Redesign
Facilities Services
Project
Logo Redesign
Ground Level View
Project Progress: | Complete
Project Status as of: | 2015-06-01
% Complete: | 100%
Target Date: | 2015-05-30
Proposed Rating: | Meets
Project Manager: | Jon Pask |  | Project Summary:
Team Members:
Jannette
Candice
Muyshann |  |  | Project Budget: | 7000
Alan |  |  | Days Left: | -2
Current Status:
Closed & Completed
Next Steps:
To…
Current Concern/Problem:
The problem is…
Potential Resolution:
I plan to…
Task Name | Resources | Duration | Start | Finish | % Work Complete
Phase 1- Define & Initiate
Kick Off Meeting |  |  | 2015-02-13 | 2015-02-13 | 100%
Vendor Meeting |  |  | 2015-03-01 | 2015-03-01 | 100%
Vendor Meeting 2 |  |  | 2015-03-09 | 2015-03-09 | 100%
Meeting minutes | Jannette |  | 2015-03-01 | 2015-04-30 | 100%
Phase 2 - Planning
Approval to Process Stationary Orders | Candice |  | 2015-03-09 | 2015-03-09 | 100%
Candice to Meet With Jose | Candice |  | 2015-03-11 | 2015-03-11 | 100%
Phase 3 - Execute
Order Stationary, BC, Mints, Signage | Jannette |  | 2015-03-17 | 2015-03-17 | 100%
Review/Approve Proofs | Muyshann |  | 2015-03-19 | 2015-03-19 | 100%
Order Mugs/Jars |  |  |  |  | 100%
Phase 4 - Monitor & Control
Receive New Logo Items/Inspect | Jannette |  | 2015-04-06 | 2015-04-30 | 100%
Revise Cards | Tina |  | 2015-04-15 | 2015-04-30 | 100%
Phase 5 - Closing
Sign Installation |  |  | 2015-04-10 | 2015-04-17 | 100%
Remove Old Stationary Supplies | Alan |  | 2015-04-13 | 2015-04-14 | 100%
Goal 1 - Meets Requirements
See goals. Part of Procuremnet Program Goals
Goal 2 - Exceeds Requirements
Goal 3 - Outstanding
Bi-Weekly Update History
Prepare an analysis of current stationary, pricing, and procure new supplies for the Bank’s Logo redesign campaign. Once approved execute tasks.

## FS-JC Space Refresh
Facilities Services
Project
Jersey City Space Refresh
Ground Level View
Project Progress: | Target
Project Status as of: | 2015-07-08
% Complete: | 50%
Target Date: | 2015-10-30
Proposed Rating: | Meets
Project Manager: | Will Williams |  | Project Summary:
Team Members:
|  |  | Project Budget: | 2420
|  |  | Days Left: | 114
Current Status:
Received proposal for new carpet.
Marble floor done, need to speak to Nicole about it.
Next Steps:
To…
Current Concern/Problem:
Potential Resolution:
Task Name | Resources | Duration | Start | Finish | % Work Complete
Vendor Proposals |  |  |  | 2015-04-30 | 100%
Vendor Selection |  |  |  | 2015-05-31 | 100%
Approval |  |  |  | 2015-06-30 | 50%
Schedule and coordinate work with trades |  |  |  | 2015-08-31 | 50%
Ensure all work is completed |  |  |  | 2015-09-30
Goal 1 - Meets Requirements
All deliverables are satisfactorily completed
Project completed within the required timeframe and with minimum disruption to Bank operations
Goal 2 - Exceeds Requirements
Project is completed ahead of schedule.
Additional facilities enhancements NOT in scope are recommended and completed without impacting the departmental budget
Goal 3 - Outstanding
(Not in scope for this goal)
Bi-Weekly Update History
Current Status: |  |  |  |  | 2015-07-08
Received proposal for new carpet.
Marble floor done, need to speak to Nicole about it.
Obtain pricing to replace carpets and buff marble tiles in the main hallways of the Jersey City office. Post approval; coordinate all activities with minimal disruption to business operations.

## FS-Lawson Training
Facilities Services
Project
Lawson Training (RQC & SME)
Ground Level View
Project Progress: | Behind
Project Status as of: | 2015-06-30
% Complete: | 20%
Target Date: | 2015-12-31
Proposed Rating: | Meets
Project Manager: | Joe Lusardi |  | Project Summary:
Team Members:
Tina Ford
Will Williams
Jon Pask |  |  | Project Budget: | 0
Joe Lusardi |  |  | Days Left: | 184
Eric Gonzalez
Current Status:
User Guides were rolled-out to CS pilot group by 6/18
Next Steps:
Obtain pilot group feedback 6/26
Investigate distribution options by 6/30
Current Concern/Problem:
Need feedback form pilot group
Potential Resolution:
Will follow up at 78/2 staff meeting
Task Name | Resources | Duration | Start | Finish | % Work Complete
Training Manual |  |  |  | 2015-04-30 | 80%
Proposal of options to deliver training (hand-out, class-setting, etc.) |  |  |  | 2015-06-30
Training Schedule |  |  |  | 2015-07-31
Goal 1 - Meets Requirements
See Goals on Procurement Purchasing Program
Goal 2 - Exceeds Requirements
Goal 3 - Outstanding
Current Status:
User Guides were rolled-out to CS pilot group by 6/18
Next Steps:
Obtain pilot group feedback 6/26
Investigate distribution options by 6/30
Current Concern/Problem:
The problem is…
Potential Resolution:
I plan to…
Bi-Weekly Update History
Review the current state of the Purchasing and Requisition modules of Lawson. Determine Bank requirements and research viable options for the future state of the Purchasing system. Include review of current Info system and plans for upgrade, and stand alone purchasing applications

## FS-Lawson PO & RQL Future
Facilities Services
Project
Lawson PO and RQL Future State
Ground Level View
Project Progress: | Target
Project Status as of: | 2015-06-30
% Complete: | 20%
Target Date: | 2015-10-31
Proposed Rating: | Meets
Project Manager: | Joseph Lusardi |  | Project Summary:
Team Members:
Janette Gonzalez
Jon Pask
|  |  | Project Budget: | 0
|  |  | Days Left: | 123
Current Status:
On-Track
Next Steps:
Implement BPRP
Begin Requirement Analysis
Current Concern/Problem:
Potential Resolution:
I plan to…
Task Name | Resources | Duration | Start | Finish | % Work Complete
Requirements Analysis |  |  |  | 2015-08-30
Identify one standalone Purchasing and Requisition module platform |  |  |  | 2015-09-30
Future State Research Plan |  |  |  | 2015-12-30
Goal 1 - Meets Requirements
See Goals, Part of Procurement Program Goals
Goal 2 - Exceeds Requirements
See Goals, Part of Procurement Program Goals
Goal 3 - Outstanding
(Not in scope for this goal)
Bi-Weekly Update History
Develop and support procuremrnt componemets that are sustainable and in aligment with objectives.

## OMWI-2014 Status Report
OMWI
Project
2014 Status Report
Ground Level View
Project Progress: | Complete
Project Status as of: | 2015-05-28
% Complete: | 100%
Target Date: | 2015-02-28
Proposed Rating: | Meets
Project Manager: | Mark Noonan |  | Project Summary:
Team Members:
Joe Lusardi
Eric Gonzalez
Noemi Rivera-Mendez |  |  | Project Budget: | 0
Khadijah Mitchell |  |  | Days Left: | -89
Current Status:
This project is complete
Next Steps:
To… | N/A
Current Concern/Problem:
The problem is… | N/A
Potential Resolution:
I plan to… | N/A
Task Name | Resources | Duration | Start | Finish | % Work Complete
Phase 1 - Initiation
Initial OMWI Meeting | Candice Soldano, Philip Scott, Eric Gonzalez, Edwin Artuz, Mark Noonan |  |  | 2014-12-19 | 100%
Phase 2 - Planning
Send Vendor Data to CVM Solutions for "Data Scrub" to locate OMWI vendors used in 2014 (this should actually happen earlier, before Thanksgiving) | Eric Gonzalez, Mark Noonan |  |  | 2014-12-20 | 100%
Discussion of Capital Markets information | Mark Noonan, Lou Solimine |  |  | 2014-12-29 | 100%
Request HelpDesk Create an OMWI Folder on the S Drive and give "Write" access to the necessary Team Members | Mark Noonan, Philip Scott, Eric Gonzalez, Edwin Artuz, Lou Solimine, Noemi Rivera-Mendez |  |  | 2015-01-02 | 100%
Place prior year's OMWI Report in the new OMWI folder on the S Drive | Mark Noonan |  |  | 2015-01-02 | 100%
Send out an email to Team Members asking that they provide "redline" feedback to the document | Mark Noonan |  |  | 2015-01-02 | 100%
Check document to see if any "redline" feedback has been given. If not, send out a follow-up email to the necessary Team Members reminding them of impending deadline | Mark Noonan |  |  | 2015-01-12 | 100%
Check document again, ask Team Members to include any necessary documentation (ie charts, graphs, numbers) for the report appendix | Mark Noonan |  |  | 2015-01-20 | 100%
Phase 3 - Execute
Begin to piece together the Report and focus on sections that are lacking, follow up with necessary Team Members | Mark Noonan |  |  | 2015-01-20 | 100%
Receive CVM Data Scrub info, Facilities Services works thru the data | Eric Gonzalez |  |  | 2015-01-21 | 100%
Receive final CVM numbers from Facilities Services | Eric Gonzalez, Mark Noonan |  |  | 2015-01-27 | 100%
Deliver Report (Draft #1) to impartial outside Team Member (Person To Be Determined) for edit | Mark Noonan, Person TBD |  |  | 2015-01-30 | 100%
Deliver Report (Draft #2) to OMWI Director for review | Mark Noonan, Edwin Artuz |  |  | 2015-02-04 | 100%
Make changes per OMWI Director feedback | Mark Noonan, Edwin Artuz |  |  | 2015-02-06 | 100%
Deliver Report (Draft #3) to… | Person TBD |  |  | 2015-02-09 | 100%
Phase 4 - Monitor & Control
Deliver Report (Draft #4) to Legal (Paul Friend) and Compliance (Steve Christatos) | Mark Noonan |  |  | 2015-02-10 | 100%
Meet with Legal & Compliance | Mark Noonan |  |  | 2015-02-12 | 100%
Deliver Final Report (Final Draft) to CEO | Mark Noonan/Edwin Artuz |  |  | 2015-02-17 | 100%
Make any final changes to the Final Report | Mark Noonan, Edwin Artuz |  |  | 2015-02-23 | 100%
Email & FedEx Report | Mark Noonan |  |  | 2015-02-26 | 100%
Phase 5 - Closing
TBD: plan for future report, future initiatives | Edwin Artuz, Mark Noonan |  |  | 2015-03-01 | 100%
Goal 1 - Meets Requirements
Goal 2 - Exceeds Requirements
Goal 3 - Outstanding
Bi-Weekly Update History
To complete the annual OMWI status report in compliance with the regulation.

## OMWI-2015 Report Planning
OMWI
Project
2015 Status Report Planning
Ground Level View
Project Progress: | Target
Project Status as of: | 2015-07-01
% Complete: | 40%
Target Date: | 2015-12-31
Proposed Rating: | Meets
Project Manager: | Mark Noonan |  | Project Summary:
Team Members:
|  |  | Project Budget: | 0
|  |  | Days Left: | 183
Current Status:
This project is currently in the planning stages
Next Steps:
To develop a system to keep all of my 2015 OMWI accomplishments together and 2016 Plans together.
Current Concern/Problem:
The problem is… | N/A
Potential Resolution:
I plan to… | N/A
Task Name | Resources | Duration | Start | Finish | % Work Complete
Phase 1- Define & Initiate
Phase 2 - Planning
Follow 2015 Diversity & Inclusion Plan | Edwin Artuz |  |  | 2015-05-01 | 40%
Phase 3 - Execute
Phase 4 - Monitor & Control
Phase 5 - Closing
Goal 1 - Meets Requirements
Goal 2 - Exceeds Requirements
Goal 3 - Outstanding
Bi-Weekly Update History
To plan for the 2015 annual OMWI status report.

## CorpServ-PM Program
Corporate Services
Project
Project Management Program - Master Tracker
Ground Level View
Project Progress: | Complete
Project Status as of: | 2015-06-28
% Complete: | 100%
Target Date: | 2015-06-30
Proposed Rating: | Meets
Project Manager: | Mark Noonan |  | Project Summary:
Team Members:
Virginia Kang
Eric Gonzalez
Khadijah Mitchell |  |  | Project Budget: | 0
|  |  | Days Left: | 2
Current Status:
Although a living document that will continue to be changed and enhanced, the Master Tracker is done.
Next Steps:
Meet with Mildred & Walter about their teams projects. Then brief Edwin on the team's progress and issues.
Current Concern/Problem:
Potential Resolution:
Task Name | Resources | Duration | Start | Finish | % Work Complete
Phase 1- Define & Initiate
Create Project Charter | Mark Noonan | 10 days | 2015-03-01 | 2015-03-10 | 100%
Kick-off Meeting to explain initial Plan. Get ideas and feedback. | Mark Noonan, Eric Gonzalez | 10 days | 2015-03-10 | 2015-03-20 | 100%
Meet to discuss what solutions (ie software) Team is comfortable working with. Show my basic Excel Master Tracker, get feedback. | Mark Noonan, Walter Moran | 11 days | 2015-03-20 | 2015-03-31 | 100%
Meet to discuss what solutions (ie software) employees are comfortable working with. Show my basic Excel Master Tracker, get feedback. | Mark Noonan, Mildred Tse-Gonzalez | 6 days | 2015-03-25 | 2015-03-31 | 100%
Phase 2 - Planning
Using the 2015 Corporate Services Goals, add a "Special Projects" section to that document | Mark Noonan | 7 days | 2015-03-25 | 2015-04-01 | 100%
Confer with Edwin on Template - gain feedback | Mark Noonan, Edwin Artuz | 3 days | 2015-04-01 | 2015-04-03 | 100%
Make a big list of all projects for HR, Facilities, OMWI - confer with Team Members on validity of list | Mark Noonan, Mildred Tse-Gonzalez, Walter Moran, Edwin Artuz | 10 days | 2015-04-05 | 2015-04-15 | 100%
Learn MS Project 2013 - NYU Classes April 11-25 - Learn about project tracking, reporting, and subprojects | Mark Noonan | 10 days | 2015-04-15 | 2015-04-25 | 100%
Using the 2015 Corporate Services Goals, and the MS Project 2013 tools, develop a Master Tracker: enter in all of the high level information. | Mark Noonan | 11 days | 2015-04-20 | 2015-05-01 | 100%
Have Project Managers enter in all of their details into each Project, down to the Task level | Mark Noonan, Project Managers | 15 days | 2015-05-01 | 2015-05-15 | 100%
Establish important dates, milestones, vendors, team members, etc for each project. Confer with HR, Facilities, and OMWI | Mark Noonan, Mildred Tse-Gonzalez, Walter Moran | 5 days | 2015-05-15 | 2015-05-20 | 100%
Confer with Edwin on this new Template - gain feedback on all of the information linking and matching up. | Mark Noonan, Edwin Artuz | 2 days | 2015-05-20 | 2015-05-22 | 100%
If necessary: Basic Tutorial on MS Project 2013 for Mildred & Walter on how to make changes/update their project's progress. | Mark Noonan, Mildred Tse-Gonzalez, Walter Moran | 5 days | 2015-05-20 | 2015-05-25 | 100%
Test out the Prototype with Mildred & Walter. | Mark Noonan, Mildred Tse-Gonzalez, Walter Moran | 6 days | 2015-05-25 | 2015-05-31 | 100%
Goal 1 - Meets Requirements
Phase 3 - Execute
Master Tracker in use by HR, Facilities Services, and OMWI | Mark Noonan, Mildred Tse-Gonzalez, Walter Moran, Eric Gonzalez | 15 days | 2015-06-01 | 2015-06-15 | 100%
Phase 4 - Monitor & Control
Get feedback from HR, Facilities, Corporate Services | Mark Noonan | 15 days | 2015-06-15 | 2015-06-30 | 100%
Add Special Projects to the Tracker as they arise | Mark Noonan |  |  | Ongoing
Update and report on progress of each project on a weekly basis | Mark Noonan, Mildred Tse-Gonzelez, Walter Moran | 15 days | 2015-06-15 | 2015-06-30 | 100%
Phase 5 - Closing
TBD: plan for future initiatives | Mark Noonan | 15 days | 2015-06-15 | 2015-06-30
Goal 2 - Exceeds Requirements
Bi-Weekly Update History
Current Status: |  |  |  |  | 2015-06-15
This project is almost done. Teams have entered in their information.
Next Steps:
Deliver a first report of the master tracker to Edwin.
Current Concern/Problem:
Still working on the possible Macro with Daniel Kohn.
Potential Resolution:
Follow up concerning the Macro.
To develop a project tracking and reporting tool for Corporate Services.

## Misc - Links&Charts
Progress of Major Projects
Schedule | Progress of All Projects | Major
Ahead | 0 | Ahead | 0
Target | 19 | Target | 12
Behind | 1 | Behind | 0
Stuck | 0 | Stuck | 0
Complete | 6 | Complete | 0
|  | Total | 12
Schedule | Progress of Projects | Schedule | Progress of Special Projects
Ahead | 0 | Ahead | 0
Target | 7 | Target | 0
Behind | 1 | Behind | 0
Stuck | 0 | Stuck | 0
Complete | 6 | Complete | 0

## Misc - How To Info
How to Information
For Project Managers
Step 1 | Following the format (see Real Estate project by Eric Gonzalez or my projects), enter in your Project Summary, Team Members, and Budget (if applicable)
Step 2 | Enter in all of your Tasks and Goals and Dates they are due.
Step 3 | Enter in the high level items: Progress, Status Date, % Complete, Target Date, Rating.
Step 4 | Enter in your Current Status, Next Steps, Current Problem, Potential Resolution.
Step 5 | Copy and Paste your 4 Current Status Items at the bottom of the page (Bi-weekly update) with the date you copy and pasted them (to keep a history).
Step 6 | Make updates Twice a Month: on the 1st of the Month and the 15th of the Month.
Step 7 | Do NOT make changes to the Master Tracker page! Ever!