## All Projects
People Ops
2018 ALL PROJECTS
Overview
Team | Project | Project Manager | Project Type | Progress | Proposed Rating | Target Date | Days Left | % Complete | Dashboard
Human Resources | Employer Branding Initiative | Amanda Lasky | Major | Target | Meets | 2018-10-31 | 141 | 30%
Human Resources | Learning & Development (Version 2.0) | Jhenene Louis | Major | Ahead | Meets | 2018-10-31 | 141 | 30%
Human Resources | Revamp Culture Club | Vanessa Macias | Major | Ahead | Meets | 2018-08-31 | 80 | 50%
Human Resources | New Manager Process | Caitlin Wilterdink | Major | Behind | Meets | 2018-06-15 | 3 | 10%
Recruiting | Internal Recruiting | Vanessa Macias | Major | Ahead | Meets | 2018-06-30 | 18 | 30%
Human Resources | Diversity & Inclusion Partnering | Krysta Kucinski | Major | Target | Meets | 2018-12-31 | 202 | 20%
Human Resources | Goal Setting Training | Jhenene Louis | Major | Ahead | Meets | 2018-10-31 | 141 | 10%
Human Resources | Manager Scorecard | Amanda Lasky | Major | Ahead | Meets | 2018-06-07 | -5 | 10%
Human Resources | Recognition | Vanessa Macias | Major | Ahead | Meets | 2018-10-31 | 141 | 10%
Facilities Services | Soundproofing Conference Rooms | Ronaldo Sakdalan | Major | Ahead | Meets | 2018-10-31 | 141 | 10%
Facilities Services | Food - Lunch Revamp | Jhenene & Ron | Major | Ahead | Meets | 2018-10-31 | 141 | 10%
IT | Asset Management / Apple Leasing | Paul Gelot | Major | Stuck | Meets | 2018-09-05 | 85 | 30%
Human Resources | Health & Wellness | Jhenene Louis | Project | Behind | Meets | 2018-10-31 | 141 | 10%
Facilities Services | Office Ticketing System (Zendesk) | Paul Gelot | Project | Behind | Meets | 2018-06-22 | 10 | 10%
IT | Finalize Onboarding | Paul Gelot | Project | Behind | Meets | 2018-10-31 | 141 | 75%
Facilities Services | Rug & Upholstery Cleaning | Ronaldo Sakdalan | Project | Ahead | Meets | 2018-06-30 | 18 | 30%
Facilities Services | Phone Booths Cell Coverage | Mark Noonan | Project | Stuck | Meets | 2018-06-30 | 18 | 80%
IT | Single Sign On (SSO) | Paul Gelot | Project | Target | Meets | 2018-09-05 | 85 | 40%
Human Resources | GDPR | Cailtin Wilterdink | Project | Target | Meets | 2018-12-31 | 202 | 0%
Human Resources | Anti-Harassment Legislation | Kelly O'Brien | Project | Target | Meets | 2018-10-09 | 119 | 0%
Human Resources | Self-Identification Survey | Kelly O'Brien | Project | Target | Meets | 2018-06-01 | -11 | 50%
Human Resources | Mentor Program | Kelly O'Brien | Project | Target | Meets | 2018-08-31 | 80 | 20%
Human Resources | KRK - Spring Branding in Krakow | Agnieszka Tomczak | Project | Ahead | Meets | 2018-12-31 | 202 | 20%
Human Resources | TBD #6 | TBD | Project | Complete | Meets | 2018-12-31 | 202 | 0% | Project Goals On Track for…
Human Resources | TBD #7 | TBD | Project | Complete | Meets | 2018-12-31 | 202 | 0% |  | Meets | Exceeds | Outstanding
Facilities Services | TBD #1 | TBD | Project | Complete | Meets | 2018-12-31 | 202 | 0% | Human Resources | 16 | 0 | 0
[9 empty] | Facilities Services | 6 | 0 | 0
Human Resources | TBD | TBD | Special | TBD |  |  |  |  | IT | 3 | 0 | 0
Facilities Services | TBD | TBD | Special | TBD |  |  |  |  | Recruiting | 1 | 0 | 0
[9 empty] | Total | 26 | 0 | 0
Project Breakdown by Team & Project
[10 empty] | Major | Project | Special | Total
[9 empty] | Human Resources | 8 | 8 | 1 | 17
[9 empty] | Facilities Services | 2 | 4 | 1 | 7
[9 empty] | IT | 1 | 2 | 0 | 3
[9 empty] | Recruiting | 1 | 0 | 0 | 1
[9 empty] | Total | 12 | 14 | 2 | 28
Formulas:
Days Left = [Target Date]-(TODAY())

## HR-Employer Branding
Human Resources
Major Project
Employer Branding Initiative
Ground Level View
Project Progress: | Target
Project Status as of: | 2018-05-01
% Complete: | 30%
Target Date: | 2018-10-31
Proposed Rating: | Meets
Project Manager: | Amanda Lasky |  | Project Summary:
Team Members: | Pam Roberts
Kelly O'Brien
Caitlin Wilterdink
| Scott Amenta |  | Project Budget: | 0
|  |  | Days Left: | 183
Current Status:
Completed final brainstorming session.
Next Steps:
Schedule meeting with Liv to discuss copy.
Current Concern/Problem:
N/A or Write here...
Potential Resolution:
I plan to…
Task Name | Resources | Duration | Start | Finish | % Work Complete
TASKS | OWNER |  | Date Assigned | Date Due | Percentage Complete
Bi-Weekly Update History
To define Spring’s Employer Brand: what current and future employees say and feel about Spring as an employer.

## HR-Learning & Development
Human Resources
Major Project
Learning & Development (Version 2.0)
Ground Level View
Project Progress: | Ahead
Project Status as of: | 2018-05-01
% Complete: | 30%
Target Date: | 2018-10-31
Proposed Rating: | Meets
Project Manager: | Jhenene Louis |  | Project Summary:
Team Members: | Pam Roberts
|  |  | Project Budget: | 0
|  |  | Days Left: | 183
Current Status:
What's the latest update. Write here...
Next Steps:
What will you be doing next. Write here...
Current Concern/Problem:
N/A or Write here...
Potential Resolution:
I plan to…
Task Name | Resources | Duration | Start | Finish | % Work Complete
TASKS | OWNER |  | Date Assigned | Date Due | Percentage Complete
Bi-Weekly Update History
Write summary…

## HR-Revamp Culture Club
Human Resources
Major Project
Revamp Culture Club
Ground Level View
Project Progress: | Ahead
Project Status as of: | 2018-05-15
% Complete: | 50%
Target Date: | 2018-08-31
Proposed Rating: | Meets
Project Manager: | Vanessa Macias |  | Project Summary:
Team Members: | Pam Roberts
Mark Noonan
|  |  | Project Budget: | 200
|  |  | Days Left: | 108
Current Status:
Waiting for confirmation of 3 events from Obi
Next Steps:
Once events are confirmed, send email to employees with events
Current Concern/Problem:
Potential Resolution:
Task Name | Resources | Duration | Start | Finish | % Work Complete
TASKS | OWNER |  | Date Assigned | Date Due | Percentage Complete
Bi-Weekly Update History
Bringing a refresh to Culture Club with new initiatives, such as volunteering

## HR-New Manager Process
Human Resources
Major Project
New Manager Process
Ground Level View
Project Progress: | Behind
Project Status as of: | 2018-05-22
% Complete: | 10%
Target Date: | 2018-06-15
Proposed Rating: | Meets
Project Manager: | Caitlin Wilterdink |  | Project Summary:
Team Members: | Caitlin Wilterdink
Project Budget:
|  |  | Days Left: | 24
Current Status:
What's the latest update. Write here...
Next Steps:
What will you be doing next. Write here...
Current Concern/Problem:
N/A or Write here...
Potential Resolution:
I plan to…
Task Name | Resources | Duration | Start | Finish | % Work Complete
TASKS | OWNER |  | Date Assigned | Date Due | Percentage Complete
Onboarding as a Manager | Caitlin |  |  |  | 100%
Managing existing Employees | Caitlin |  |  | 2018-06-15 | 0%
Offboarding Employees | Caitlin |  |  | 2018-06-15 | 0%
Bi-Weekly Update History
Create training materials for Mgrs at Spring

## REC-Internal Recruiting
Human Resources
Major Project
Internal Recruiting
Ground Level View
Project Progress: | Ahead
Project Status as of: | 2018-05-01
% Complete: | 30%
Target Date: | 2018-06-30
Proposed Rating: | Meets
Project Manager: | Vanessa Macias |  | Project Summary:
Team Members: | Caitlin Wilterdink
Pam Roberts
|  |  | Project Budget: | 0
|  |  | Days Left: | 60
Current Status:
Waiting for feedback on drafted proposal from Kelly & Pam
Next Steps:
Once feedack is in, create version 2 of draft
Current Concern/Problem:
N/A or Write here...
Potential Resolution:
I plan to…
Task Name | Resources | Duration | Start | Finish | % Work Complete
TASKS | OWNER |  | Date Assigned | Date Due | Percentage Complete
Bi-Weekly Update History
Revamp the existing Referral Policy

## HR-D&I Partnering
Human Resources
Major Project
Diversity & Inclusion Partnering
Ground Level View
Project Progress: | Target
Project Status as of: | 2018-06-05
% Complete: | 20%
Target Date: | 2018-12-31
Proposed Rating: | Meets
Project Manager: | Krysta Kucinski |  | Project Summary:
Team Members: | Caitlin Wilterdink
|  |  | Project Budget: | 0
|  |  | Days Left: | 209
Current Status:
Tech Inclusion emails sent last week, exec approved, volunteering is open and sign ups occurred. Met with NYC/KRK eng regarding onsite reboot to gather feedback and discuss next steps.
Next Steps:
Review at recruiting weekly. Final interation on the onsite reboot proposal. Set up meeting with Satwik for next week to discuss.
Current Concern/Problem:
N/A
Potential Resolution:
N/A
Task Name | Resources | Duration | Start | Finish | % Work Complete
Subprojects | OWNER |  | Date Assigned | Date Due | Percentage Complete
Recruiting process redesign | Krysta |  | 2018-05-02 | 2018-06-15 | 25%
Whiteboarding v Tech Environment | Krysta |  | 2018-05-02 | TBD | 20%
Research D&I events | Krysta |  | 2018-05-02 | Ongoing | 10%
D & I Presentation | Caitlin |  | 2018-05-02 | 2018-05-25 | 90%
Bi-Weekly Update History
Write summary...
To improve recruiting processes and include current employees on D&I related initiatives.

## HR-Goal Setting Training
Human Resources
Major Project
Goal Setting Training
Ground Level View
Project Progress: | Ahead
Project Status as of: | 2018-05-01
% Complete: | 10%
Target Date: | 2018-10-31
Proposed Rating: | Meets
Project Manager: | Jhenene Louis |  | Project Summary:
Team Members: | Kelly O'Brien
Project Budget:
|  |  | Days Left: | 183
Current Status:
What's the latest update. Write here...
Next Steps:
What will you be doing next. Write here...
Current Concern/Problem:
N/A or Write here...
Potential Resolution:
I plan to…
Task Name | Resources | Duration | Start | Finish | % Work Complete
TASKS | OWNER |  | Date Assigned | Date Due | Percentage Complete
Bi-Weekly Update History
Write summary...

## HR-Manager Scorecard
Human Resources
Major Project
Manager Scorecard
Ground Level View
Project Progress: | Ahead
Project Status as of: | 2018-05-17
% Complete: | 10%
Target Date: | 2018-06-07
Proposed Rating: | Meets
Project Manager: | Amanda Lasky |  | Project Summary:
Team Members: | Kelly O'Brien
Project Budget:
|  |  | Days Left: | 21
Current Status:
Presented to exec 5/24
Next Steps:
Feedback sessions between Pam/Amanda/Kelly
Current Concern/Problem:
N/A or Write here...
Potential Resolution:
I plan to…
Task Name | Resources | Duration | Start | Finish | % Work Complete
TASKS | OWNER |  | Date Assigned | Date Due | Percentage Complete
Bi-Weekly Update History
To create a survey that captures information, providing actionable feedback to help People Managers develop and grow.

## HR-Recognition
Human Resources
Major Project
Recognition
Ground Level View
Project Progress: | Ahead
Project Status as of: | 2018-05-01
% Complete: | 10%
Target Date: | 2018-10-31
Proposed Rating: | Meets
Project Manager: | Vanessa Macias |  | Project Summary:
Team Members: | Kelly O'Brien |  | We want to create a recognition program across the org that allows for recognition where it is due
Mark
|  |  | Project Budget: | 0
|  |  | Days Left: | 183
Current Status:
Met with Kelly & Mark 6.6.18
Next Steps:
Vanessa to draft a proposal that Pam can share with offsite members who are interested
Current Concern/Problem:
N/A or Write here...
Potential Resolution:
I plan to…
Task Name | Resources | Duration | Start | Finish | % Work Complete
TASKS | OWNER |  | Date Assigned | Date Due | Percentage Complete
Bi-Weekly Update History

## FS-Soundproofing
Facilities Services
Major Project
Soundproofing Conference Rooms
Ground Level View
Project Progress: | Ahead
Project Status as of: | 2018-05-01
% Complete: | 10%
Target Date: | 2018-10-31
Proposed Rating: | Meets
Project Manager: | Ron Sakdalan |  | Project Summary:
Team Members: | Mark Noonan
|  |  | Project Budget: | 0
|  |  | Days Left: | 183
Current Status:
What's the latest update. Write here...
Next Steps:
What will you be doing next. Write here...
Current Concern/Problem:
N/A or Write here...
Potential Resolution:
I plan to…
Task Name | Resources | Duration | Start | Finish | % Work Complete
TASKS | OWNER |  | Date Assigned | Date Due | Percentage Complete
Bi-Weekly Update History
Write summary...

## FS-Food Lunch Revamp
Facilities Services
Major Project
Food - Lunch Revamp
Ground Level View
Project Progress: | Ahead
Project Status as of: | 2018-05-01
% Complete: | 10%
Target Date: | 2018-10-31
Proposed Rating: | Meets
Project Manager: | Jhenene & Ron |  | Project Summary:
Team Members: | Mark Noonan
|  |  | Project Budget: | 0
|  |  | Days Left: | 183
Current Status:
What's the latest update. Write here...
Next Steps:
What will you be doing next. Write here...
Current Concern/Problem:
N/A or Write here...
Potential Resolution:
I plan to…
Task Name | Resources | Duration | Start | Finish | % Work Complete
TASKS | OWNER |  | Date Assigned | Date Due | Percentage Complete
Bi-Weekly Update History
Working with different vendors such as Grubhub,Forkable, and Eat24.

## IT-Asset ManagementApple Leasin
IT
Major Project
Asset Management / Apple Leasing
Ground Level View
Project Progress: | Stuck
Project Status as of: | 2018-05-01
% Complete: | 30%
Target Date: | 2018-10-31
Proposed Rating: | Meets
Project Manager: | Paul Gelot |  | Project Summary:
Team Members: | Mark Noonan |  | A solution for managing IT inventory & option to lease machines from Apple instead of purchasing
Justin Lintz
|  |  | Project Budget: | 0
|  |  | Days Left: | 183
Current Status:
Asset management options ongoing. Leasing is stuck because Apple's financing wants 3 months of band statements which finance will not release.
Next Steps:
Continue Asset management testing. Put leasing on hold until after fundraising is over. Keep purchasing machines for now.
Current Concern/Problem:
Leasing would save money, so we are not helping ourselves here.
Potential Resolution:
I plan to wait...
Task Name | Resources | Duration | Start | Finish | % Work Complete
TASKS | OWNER |  | Date Assigned | Date Due | Percentage Complete
Bi-Weekly Update History

## HR-Health & Wellness
Human Resources
Project
Health & Wellness Initiatives
Ground Level View
Project Progress: | Behind
Project Status as of: | 2018-05-01
% Complete: | 10%
Target Date: | 2018-10-31
Proposed Rating: | Meets
Project Manager: | Jhenene Louis |  | Project Summary:
Team Members: | Mark Noonan
Kelly O'Brien
|  |  | Project Budget: | 0
|  |  | Days Left: | 183
Current Status:
What's the latest update. Write here...
Next Steps:
What will you be doing next. Write here...
Current Concern/Problem:
N/A or Write here...
Potential Resolution:
I plan to…
Task Name | Resources | Duration | Start | Finish | % Work Complete
TASKS | OWNER |  | Date Assigned | Date Due | Percentage Complete
Bi-Weekly Update History
Write summary...

## FS-Office Ticketing System
Facilities Services
Project
Office Ticketing System (Zendesk)
Ground Level View
Project Progress: | Behind
Project Status as of: | 2018-05-01
% Complete: | 10%
Target Date: | 2018-10-31
Proposed Rating: | Meets
Project Manager: | Paul Gelot |  | Project Summary:
Team Members: | Ronaldo Sakdalan
Mark Noonan
|  |  | Project Budget: | 0
|  |  | Days Left: | 183
Current Status:
What's the latest update. Write here...
Next Steps:
What will you be doing next. Write here...
Current Concern/Problem:
N/A or Write here...
Potential Resolution:
I plan to…
Task Name | Resources | Duration | Start | Finish | % Work Complete
TASKS | OWNER |  | Date Assigned | Date Due | Percentage Complete
Bi-Weekly Update History
Write summary...

## IT-Finalize Onboarding
IT
Project
Finalize Onboarding
Ground Level View
Project Progress: | Behind
Project Status as of: | 2018-05-01
% Complete: | 10%
Target Date: | 2018-10-31
Proposed Rating: | Meets
Project Manager: | Paul Gelot |  | Project Summary:
Team Members: | Mark Noonan
Project Budget:
|  |  | Days Left: | 183
Current Status:
What's the latest update. Write here...
Next Steps:
What will you be doing next. Write here...
Current Concern/Problem:
N/A or Write here...
Potential Resolution:
I plan to…
Task Name | Resources | Duration | Start | Finish | % Work Complete
TASKS | OWNER |  | Date Assigned | Date Due | Percentage Complete
Bi-Weekly Update History
Write summary...

## FS-RugUpholstery Cleaning
Facilities Services
Project
Rug & Upholstery Cleaning
Ground Level View
Project Progress: | Behind
Project Status as of: | 2018-05-01
% Complete: | 10%
Target Date: | 2018-10-31
Proposed Rating: | Meets
Project Manager: | Ronaldo Sakdalan |  | Project Summary:
Team Members: | Mark Noonan
|  |  | Project Budget: | 2000
|  |  | Days Left: | 183
Current Status:
What's the latest update. Write here...
Next Steps:
What will you be doing next. Write here...
Current Concern/Problem:
N/A or Write here...
Potential Resolution:
I plan to…
Task Name | Resources | Duration | Start | Finish | % Work Complete
TASKS | OWNER |  | Date Assigned | Date Due | Percentage Complete
Bi-Weekly Update History
Write summary...

## FS-Phone Booths Cell Coverage
Facilities Services
Project
Phone Booths Cell Coverage
Ground Level View
Project Progress: | Stuck
Project Status as of: | 2018-06-05
% Complete: | 80%
Target Date: | 2018-06-30
Proposed Rating: | Meets
Project Manager: | Mark Noonan |  | Project Summary:
Team Members: | Ronaldo Sakdalan
Paul Gelot
|  |  | Project Budget: | 0
|  |  | Days Left: | 25
Current Status:
Got a mini tower from Verizon.
Next Steps:
Need to hook up the HR team to it.
Current Concern/Problem:
Need to activate a port in order to get this up and running.
Potential Resolution:
Paul/Justin to resolve. Mark sidetracked by Olympics. Will prioritize upon completion.
Task Name | Resources | Duration | Start | Finish | % Work Complete
TASKS | OWNER |  | Date Assigned | Date Due | Percentage Complete
Bi-Weekly Update History
A solution to fix the poor cell phone coverage in the phone booths.

## IT-Single Sign On
IT
Project
Single Sign On (SSO)
Ground Level View
Project Progress: | Behind
Project Status as of: | 2018-05-01
% Complete: | 10%
Target Date: | 2018-10-31
Proposed Rating: | Meets
Project Manager: | Paul Gelot |  | Project Summary:
Team Members: | Mark Noonan
Justin Lintz
|  |  | Project Budget: | 10000
|  |  | Days Left: | 183
Current Status:
What's the latest update. Write here...
Next Steps:
What will you be doing next. Write here...
Current Concern/Problem:
N/A or Write here...
Potential Resolution:
I plan to…
Task Name | Resources | Duration | Start | Finish | % Work Complete
TASKS | OWNER |  | Date Assigned | Date Due | Percentage Complete
Test out Okta | Paul |  |  | 2018-06-14
Bi-Weekly Update History
Prepare analysis, and provide options for implementation of SSO. Upon approval, move forward with proposed plan and execute.

## Rec- GDPR
Human Resources
Project
GDPR
Ground Level View
Project Progress: | Target
Project Status as of: | 2018-05-25
% Complete: | 0%
Target Date: | 2018-12-31
Proposed Rating: | Meets
Project Manager: | Caitlin Wilterdink |  | Project Summary:
Team Members: | Agnieszka
Krysta
|  |  | Project Budget: | 0
|  |  | Days Left: | 220
Current Status:
What's the latest update. Write here...
Next Steps:
What will you be doing next. Write here...
Current Concern/Problem:
N/A or Write here...
Potential Resolution:
I plan to…
Task Name | Resources | Duration | Start | Finish | % Work Complete
TASKS | OWNER |  | Date Assigned | Date Due | Percentage Complete
GH Process for Managing Prospects | Krysta |  |  | 2018-05-18 | 80%
GDPR Compliant GH | Caitlin
Training for Recruiting Team
Bi-Weekly Update History
Recruiting Readiness for GDPR

## HR-Anti-Harassment
Human Resources
Project
Anti-Harassment Legislation
Ground Level View
Project Progress: | Target
Project Status as of: | 2018-05-16
% Complete: | 0%
Target Date: | 2018-10-09
Proposed Rating: | Meets
Project Manager: | Kelly O'Brien |  | Project Summary:
Team Members:
Project Budget:
|  |  | Days Left: | 146
Current Status:
Have identified gaps, and working to close. Spoken to four suppliers for training.
Next Steps:
To get approval on costs.
Current Concern/Problem:
N/A or Write here...
Potential Resolution:
I plan to…
Task Name | Resources | Duration | Start | Finish | % Work Complete
TASKS | OWNER |  | Date Assigned | Date Due | Percentage Complete
Partner with D&I Council to organize training
Update Policy
Bi-Weekly Update History
Responding to recent changes in harassment legislation

## HR-Self-IdentSurvey
Human Resources
Project
Self-Indentification Survey
Ground Level View
Project Progress: | Target
Project Status as of: | 2018-05-17
% Complete: | 50%
Target Date: | 2018-06-01
Proposed Rating: | Meets
Project Manager: | Kelly O'Brien |  | Project Summary:
Team Members: | Dan
|  |  | Project Budget: | 0
|  |  | Days Left: | 15
Current Status:
Survey has been drafted, and shared with Pam, Dan and Bill for feedback
Next Steps:
Speaking with CultureAmp about setting up survey correctly in the platform. Sharing with D&I Council.
Current Concern/Problem:
N/A or Write here...
Potential Resolution:
I plan to…
Task Name | Resources | Duration | Start | Finish | % Work Complete
TASKS | OWNER |  | Date Assigned | Date Due | Percentage Complete
Speak to CultureAmp
Share with Bill and LaToya
Share with D&I Council for feedback
Share with Exec for feedback
Draft Survey in CultureAmp
Launch survey
Analyze findings
Share with D&I Council / Company / Exec
Bi-Weekly Update History
Voluntary self identification survey

## HR-MentorProgram
Human Resources
Project
Mentor Program
Ground Level View
Project Progress: | Target
Project Status as of: | 2018-05-22
% Complete: | 20%
Target Date: | 2018-08-31
Proposed Rating: | Meets
Project Manager: | Kelly O'Brien |  | Project Summary:
Team Members: | Amanda
|  |  | Project Budget: | 0
|  |  | Days Left: | 101
Current Status:
Draft outline completed. Amanda joined the project!
Next Steps:
Finalize the proposal.
Current Concern/Problem:
Potential Resolution:
Task Name | Resources | Duration | Start | Finish | % Work Complete
TASKS | OWNER |  | Date Assigned | Date Due | Percentage Complete
Bi-Weekly Update History
Mentorship program for all employees.

## HR-KRK-SpringBranding
Human Resources
Project
Spring Branding in Krakow
Ground Level View
Project Progress: | Ahead
Project Status as of: | 2018-05-16
% Complete: | 20%
Target Date: | 2018-12-31
Proposed Rating: | Meets
Project Manager: | Agnieszka Tomczak |  | Project Summary:
Team Members: |  |  | To make Spring more popular in Kraków in order to reach out to more experienced engineers and bring them on board
|  |  | Project Budget: | 0
|  |  | Days Left: | 229
Current Status:
Looking for more possible meetups to join. Talked to few engineers, they are interested in presenting during an event, especially Piotr who has some experience. Going to Python meetup in two weeks.
Next Steps:
Look for more meetups and events organised by other IT companies in Krakow and try to join. Figure out couple of posts before setting the facebook page.
Current Concern/Problem:
N/A or Write here...
Potential Resolution:
I plan to…
Task Name | Resources | Duration | Start | Finish | % Work Complete
TASKS | OWNER |  | Date Assigned | Date Due | Percentage Complete
Research for meetups to join | Agnieszka Tomczak |  |  | 2018-06-30 | 10%
Facebook page for Spring Poland | Agnieszka Tomczak |  |  | 2018-06-30
Organizing a meetup/workshop | Agnieszka Tomczak |  |  | 2018-09-30
Bi-Weekly Update History

## HR-TBD#6
Human Resources
Project
TBD #6
Ground Level View
Project Progress: | Complete
Project Status as of: | 2018-05-01
% Complete: | 0%
Target Date: | 2018-12-31
Proposed Rating: | Meets
Project Manager: | TBD |  | Project Summary:
Team Members:
|  |  | Project Budget: | 0
|  |  | Days Left: | 244
Current Status:
What's the latest update. Write here...
Next Steps:
What will you be doing next. Write here...
Current Concern/Problem:
N/A or Write here...
Potential Resolution:
I plan to…
Task Name | Resources | Duration | Start | Finish | % Work Complete
TASKS | OWNER |  | Date Assigned | Date Due | Percentage Complete
Bi-Weekly Update History
Write summary...

## HR-TBD#7
Human Resources
Project
TBD #7
Ground Level View
Project Progress: | Complete
Project Status as of: | 2018-05-01
% Complete: | 0%
Target Date: | 2018-12-31
Proposed Rating: | Meets
Project Manager: | TBD |  | Project Summary:
Team Members:
|  |  | Project Budget: | 0
|  |  | Days Left: | 244
Current Status:
What's the latest update. Write here...
Next Steps:
What will you be doing next. Write here...
Current Concern/Problem:
N/A or Write here...
Potential Resolution:
I plan to…
Task Name | Resources | Duration | Start | Finish | % Work Complete
TASKS | OWNER |  | Date Assigned | Date Due | Percentage Complete
Bi-Weekly Update History
Write summary...

## FS-TBD#1
Facilities Services
Project
TBD #1
Ground Level View
Project Progress: | Complete
Project Status as of: | 2018-05-01
% Complete: | 0%
Target Date: | 2018-12-31
Proposed Rating: | Meets
Project Manager: | TBD |  | Project Summary:
Team Members:
|  |  | Project Budget: | 0
|  |  | Days Left: | 244
Current Status:
What's the latest update. Write here...
Next Steps:
What will you be doing next. Write here...
Current Concern/Problem:
N/A or Write here...
Potential Resolution:
I plan to…
Task Name | Resources | Duration | Start | Finish | % Work Complete
TASKS | OWNER |  | Date Assigned | Date Due | Percentage Complete
Bi-Weekly Update History
Write summary...

## Misc - Links&Charts
Progress of Major Projects
Schedule | Progress of All Projects | Major
Ahead | 10 | Ahead | 8
Target | 7 | Target | 2
Behind | 4 | Behind | 1
Stuck | 2 | Stuck | 0
Complete | 3 | Complete | 0
|  | Total | 11
Schedule | Progress of Projects | Schedule | Progress of Special Projects
Ahead | #REF! | Ahead | #REF!
Target | #REF! | Target | #REF!
Behind | #REF! | Behind | #REF!
Stuck | #REF! | Stuck | #REF!
Complete | #REF! | Complete | #REF!

## Misc - How To Info
How to Information
For Project Managers
Step 1 | Following the format (see Real Estate project by Eric Gonzalez or my projects), enter in your Project Summary, Team Members, and Budget (if applicable)
Step 2 | Enter in all of your Tasks and Goals and Dates they are due.
Step 3 | Enter in the high level items: Progress, Status Date, % Complete, Target Date, Rating.
Step 4 | Enter in your Current Status, Next Steps, Current Problem, Potential Resolution.
Step 5 | Copy and Paste your 4 Current Status Items at the bottom of the page (Bi-weekly update) with the date you copy and pasted them (to keep a history).
Step 6 | Make updates Twice a Month: on the 1st of the Month and the 15th of the Month.
Step 7 | Do NOT make changes to the Master Tracker page! Ever!